“Better Together”

How ASAE, GWSAE, The Center for Association Leadership, and the ASAE Foundation Created a New Business Model for the Future

Prepared by

Al Rickard, CAE

# President

ASSOCIATION VISION

www.associationvision.com

Contents

The Vision	3

Quotables	4

Better Together	5

The Beginning	6

Challenges and Success Factors	8

Not Your Average Merger	9

Seizing Momentum	11

Merger Timeline	12

Negotiations	15

Culture Issues	18

Members and Stakeholder Feedback	20

“Industry Partner” Considerations	26

Due Diligence	27

Staff Integration	28

GWSAE Member Vote Campaign	31

Communications	34

Lessons from the Merger	37

Appendix A: JOLT Member Roster

Appendix B: Merger Proposal Report and Recommendations

The Vision

“Bringing together GWSAE, The Center for Association Leadership, ASAE and the ASAE Foundation pioneers a new business model for the future. By uniting under a common vision, the new ASAE and Center will provide the association community with the leadership and tools needed to ensure that associations become a defining force in shaping the 21st century.”

- The “Better Together” Web Site, July 2004

Quotables

“Change is the law of life and those who look only to the past or present are certain to miss the future.” 
     — John F. Kennedy

“Greatness is not a function of circumstance. Greatness... is largely a matter of conscious choice.”
      — Jim Collins

“Life is either a daring adventure, or nothing.”

— Helen Keller

“Success is never final.”

— Bill Marriott, Marriott Corporation

"[In a visionary organization] the drive for progress is never satisfied with the status quo, even when the status quo is working well."
     — Jim Collins

“We cannot become what we need to be by remaining what we are."
     — Max DuPree, CEO/Chairman, Herman Miller Corp.

Better Together

The six quotes on the previous page capture much of the inspiration behind a historic event – the merger involving the American Society of Association Executives (ASAE), the Greater Washington Society of Association Executives (GWSAE), The Center for Association Leadership, and the ASAE Foundation.

Each quote connects with a critical aspect of what was a remarkable consolidation of four complementary, yet competitive, organizations. Perhaps the quote from business author Jim Collins best captured the essence of what this merger was about:

"[In a visionary organization] the drive for progress is never satisfied with the status quo, even when the status quo is working well."

All four organizations were stable, financially healthy organizations serving their own sets of constituents with a wide range of successful programs and services. None of them had to merge. Yet they chose to do so. This report examines how this merger happened, and offers insight and lessons that we hope will benefit other associations considering similar actions.

ASAE and The Center for Association Leadership are committed to offering information about this merger as a case study for the association community. In addition to this report, documents such as member and stakeholder e-mails, press releases, and materials sent to GWSAE members in the voting process are available on request. Contact Al Rickard of Association Vision at 703-402-9713 or arickard@associationvision.com.

The Beginning

When the volunteer leaders of the four primary organizations serving the association profession sat down together in the spring of 2003, they had no idea where their discussions would take them.

As members of a task force called the Joint Organizations Leadership Team (JOLT), these leaders embarked on an important mission: To address ways the organizations could work together to advance the association profession and its industry partners.

In the months to come, JOLT would make history – creating a new business model for the future that would create exciting new opportunities for the association profession.

The path before them was hardly clear. Decades of discussions about how ASAE and GWSAE could work more closely together had not generated any significant collaboration.

These two organizations competed in the world’s largest association market – the Washington, DC metropolitan area – home to more than 3,500 associations and 75,000 association employees.

For ASAE, the national organization, the Washington, DC region represented the most focused and lucrative market in the nation. For GWSAE, the regional organization, the Washington, DC region represented its entire market.

While both organizations grew and succeeded throughout the 1980s and 90s, association professionals in the Washington, DC region found their loyalties divided.

In 2001, GWSAE launched a new organization designed to provide even more resources for advanced learning and knowledge-building: The Center for Association Leadership. This new organization, structured as a subsidiary foundation of GWSAE, was not limited by the geographic scope of GWSAE. Instead, it was a boundaryless organization providing programs on a national, and even international, scale.

This new structure placed GWSAE and The Center in a stronger market position with a wider scope of programs, increasing its competition with ASAE and the ASAE Foundation. Even though competition is the basis of business success, it can also produce unwanted duplication and overlap of programs and activities. When this competition slows the potential progress of a profession, it creates an opportunity for change and growth.

This opportunity for a better future is what drove the proposed merger involving ASAE, GWSAE, The Center for Association Leadership, and the ASAE Foundation. The well-known business author Malcolm Gladwell might call it a “tipping point.”

In the summer of 2003, JOLT issued the following statement:

“It is our belief that by working together and capitalizing on the strengths of all these organizations, we will reach new heights of service and value for our members and customers.  This Joint Leadership Team will continue to meet and, in the months ahead, develop a proposal to best move forward with the ultimate goal of advancing the association management profession to which we all are deeply committed.  It is our hope that by working together, we will:

- Create greater efficiency and focus,

- Eliminate confusion in the marketplace,

- Provide more valuable services to best meet the needs of our stakeholders.”

Discussions at the volunteer level began during a time of transition for ASAE – the organization was searching for a new president and CEO. Once John H. Graham IV, CAE, was installed as president & CEO of ASAE, he and Susan Sarfati, CAE, president & CEO of GWSAE and the Center for Association Leadership, were invited to join the team. Both chief staff executives expressed immediate support for the process, believing that what was best for the profession would make the most sense for their organizations. They recognized that their respective roles were critical in developing and presenting to the volunteer leadership a workable model that could succeed.

“We began this process without knowing where it would really go,” GWSAE 2003-04 Chairman Greg Balestrero, chief executive officer of the Project Management Institute, recalled. “We didn’t know if it was even possible to invent a new reality, or if we would just end up with collaborating on a few projects.”

“Developing a closer relationship between these organizations had been on people’s minds for a long, long time, but earlier discussions had failed because it wasn’t the right time for volunteer and staff leaders,” said Tom Kuhn, ASAE 2004-05 chairman and president of the Edison Electric Institute. He added that the group talked not only about how to better serve customers inside the Washington, DC beltway, but focused on how to build a structure that was best for customers both inside and outside the beltway.

Ralph Nappi, CAE, the GWSAE chairman-elect at the time negotiations began who is now chairman of the new Center Board, observed, "It was the right time to restart the discussions. It was the perfect example of the there being a right time and a place for an idea to blossom." Nappi is president of the American Machine Tool Distributors' Association.

The roster of JOLT members is shown in Appendix A.

Challenges and Success Factors

Many mergers are driven largely by necessity, often with one of the parties under some financial duress. Not so with this merger. Although ASAE had endured some deficits in the post-9-11 era, including significant staff layoffs, its financial situation had stabilized, and the organization was now under the leadership of a new executive. The ASAE Foundation was on solid financial ground with restricted assets of $10 million, consisting primarily of a research endowment.

GWSAE and The Center for Association Leadership were in a very strong financial position with combined assets of $10 million. The Center for Association Leadership, as a foundation of GWSAE, completed its first capital campaign in 2001 and successfully raised $4.8 million.

Ironically, this absence of financial issues became a significant challenge to overcome, as some members and stakeholders, including the trade press, repeatedly questioned why the organizations should merge if there were no financial problems.

To answer this question, leaders in the merger process often answered, “If the only reason we should merge is because of finances, that’s not a good enough reason.” Their focus remained on the larger picture – what was best for the future of the profession.

Even so, this lack of a financial imperative proved to be one of the key issues to overcome in the minds of stakeholders. Overall, the primary issues to overcome regarding this merger boiled down to the following:

- No financial imperative for change

- Cultural issues

- Complexity of merging four organizations into a new structure

- Convincing GWSAE members that their interests would continue to be served

- Overcoming a fear of change

One barrier that often derails mergers – the egos of volunteer leaders and chief staff executives – was notably absent from the equation. The confluence of factors that contributed to this situation included:

- GWSAE and The Center for Association Leadership President & CEO Susan Sarfati, CAE, was sincerely committed to doing what was best for the profession, considering that more important than her position.

- ASAE President & CEO John H. Graham IV, CAE, was new in his position and was also open to exploring the best options for the future of the profession.

- Significant cross-fertilization of volunteer leaders existed among the four boards of directors – some members served on more than one board, and many others had previously served on other boards and/or had been involved in the other organizations.

Not Your Average Merger

Consolidation.

Merger.

Strategic Alliance.

Combination.

Each of these terms was used at different points in the process to describe the merger. As the exact structure unfolded, lawyers advised the organizations on the language that would be best used to describe it. In the end, it was simply identified as a “merger.”

While the shift in terminology appeared confusing to some observers, it was driven by the fact that this was not your average merger.

Most mergers involve combining two existing entities into a single organization. Not so with this one – it involved the following separate transactions:

- A consolidation of the ASAE Foundation into The Center

- Transfer of the ASAE Education Division into The Center

- The dissolution of GWSAE and transfer of its assets to The Center

To top it off, the two surviving organizations – ASAE and The Center – were billed as both “independent” and “interdependent” organizations. This terminology describes a somewhat complicated, yet politically necessary, relationship between the two entities.

In terms of governance, the two organizations are in fact independent – the boards of the respective groups control their assets and destinies, albeit with certain restrictions on their ability to separate from each other.

However, the relationship was structured to give each organization powerful incentives to support the success of the other, eliminating longstanding competition between them.

Joint governance committees for finance, audit, planning, and nominating were established. In addition, a single, unified staff structure was put in place.

Details about the structure of the merger are contained in the “Merger Proposal Report and Recommendations” document (Appendix B). This report was produced in May 2004 prior to the merger votes by the boards of the four organizations.

Staff Structure

The staff structure of the two organizations was designed to capitalize on the strengths of all four organizations and present seamless customer service to members and stakeholders. Although the staff resides at two different physical locations (ASAE headquarters and The Center headquarters) located a few blocks apart in the heart of Washington, DC, communication and information technology systems were integrated to support a staff that operates as a unified entity.

All staff are ASAE employees and fall into three groups within the overall operation:

- ASAE Staff

- Center Staff

- “Shared Services” Staff

ASAE staff and Center staff are devoted to programs run by their respective organizations. Recognizing that many functions are common to both organizations, ASAE and The Center created several areas of “shared services” that are staffed by employees who serve the needs of both organizations. These areas include:

- Finance and Administration

- Human Resources

- Meetings and Expositions

- Marketing

- Public Relations and Communications

- Market Research

- Publications

Seizing Momentum

JOLT recognized that the success of the merger hinged on their ability to achieve conceptual support at the outset of the process. With this in mind, JOLT built a logical and compelling case for merging the organizations, including a 30,000-foot view of the key benefits of merger, the new organizational structure, governance, and the proposed due diligence process.

By presenting this broad conceptual outline for immediate approval by each of the four boards at the beginning of the process, JOLT allowed leaders to focus on the big picture, without making initial approval dependent on the review of myriad details.

On January 15, 2004, the boards of the four organizations convened for a joint meeting – the first such meeting in the history of the organizations – and listened to a proposal from JOLT on the merger. The boards then adjourned for separate meetings, where each considered the merits of the proposal and voted on the concept of the merger, subject to subsequent due diligence by volunteer leaders, staff, legal counsel, and auditors. All four boards voted to approve the merger concept.

This approach achieved the desired results of generating tremendous momentum towards a positive outcome, with the clear understanding that the merger was not a “done deal” until all parties were satisfied with the final structure and the results of the due diligence process.

Merger Timeline

A target date of July 1, 2004 was established for implementation of the merger, pending approval by the four boards and the GWSAE members. In setting this date, JOLT tried to strike a balance between acting quickly and allowing sufficient time for the due diligence process to be carried out. The timeframe brought the required focus to the due diligence effort.

At the same time, Graham and Sarfati explained that every aspect of the merged organizations would not take place immediately on that date. While the essential structural and program integration would begin on July 1, 2004, full implementation of the merger would be, by necessity, a gradual process involving new program development, staff integration, cultural change, and other factors that take time. Key milestones in the process included:

Spring 2003

JOLT Formed

Summer 2003

Staff CEOs Join JOLT

Fall 2003

JOLT Finalizes Merger Concept

1/15/2004

Four Boards Approve Merger Concept

- Provides impetus for proposed merger process to proceed

1/15/2004

Press Conference on Proposed Merger

- First public announcement of intent to pursue consolidation

1/16/2004

E-Mail Announcements Sent to Stakeholders

- First direct communication with stakeholders and opportunity for input

1/27/2004

ASAE-GWSAE Staff Team Meeting

- First opportunity for ASAE and GWSAE staff to meet and discuss vision and goals for merger

1/28/2004

Town Hall Meeting in Washington, DC

- First forum for direct member and stakeholder input

1/29/2004

E-Mail Update Sent to All Stakeholders

- Provided summary of comments received at the first Town Hall Meeting

2/10/2004

Town Hall Meeting in Baltimore

- Second forum for direct member and stakeholder input (mostly ASAE members)

2/11/2004

E-Mail Update Sent to All Stakeholders

- Highlighted summary of very positive e-mail responses from members and stakeholders

2/18/2004

GWSAE Board Meeting

- First extensive Board discussion of proposed merger

2/25/2004

GWSAE Town Hall Meeting in Washington, DC

3/3/2004

GWSAE Town Hall Meeting in Bethesda, MD

3/4/2004

GWSAE Town Hall Meeting in Alexandria, VA

3/9/2004

GWSAE Town Hall Meeting in Tysons Corner, VA

3/13/2004

Integration Steering Committee (ISC) Staff Team Retreat

- Created common vision and values for merged organizations and strengthened the team atmosphere

3/16/2004

GWSAE Business Partners Town Hall Meeting

3/23/2004

E-Mail Sent to All GWSAE-Center Stakeholders

- Summarizes GWSAE Town Hall meetings and presents complete picture of GWSAE-Center finances

4/1/2004

ASAE Board Meeting

- Opportunity for ASAE Board to review GWSAE and Center financials

4/15/2004

Business Area Plans Completed by ISC Subcommittees

- Provided first look at how each functional area may be structured following the merger

4/22-25/2004

GWSAE Board Think Tank

- In-depth discussion of merger issues to make recommendations to JOLT

5/11/2004

JOLT Meeting

- Reviewed the proposal, negotiated final items, approved plan to be presented to the four boards

5/25/2004

Four Boards Approve Merger

- Presentation of full proposal to all four boards, each board votes separately to approve merger

5/26/2004

Press Conference Announcing Board Approvals of Merger

- Announcement of board approval and preview of process leading to GWSAE member vote

5/26/2004

E-Mail Update Sent to All Stakeholders

- Announcement of board approval and preview of process leading to GWSAE member vote

6/10/2004

Voting Information and Background Sent to GWSAE Voting Members

6/15/2004

GWSAE Member Briefing on Merger Vote in Alexandria, VA

- First in a series of three briefings designed for members to receive information and ask questions

6/16/2004

GWSAE Member Briefing on Merger Vote (Audioconference)

6/22/2004

GWSAE Member Briefing in Washington, DC

6/30/2004

GWSAE Members Approve Merger

- Members approve merger with a positive vote of 78%

6/30/2004

Press Release Sent Announcing Final Merger Approval

7/01/2004

E-Mails Sent to Members and Stakeholders Announcing Final Merger Approval

Negotiations

Merger negotiations are never easy.

The negotiations to finalize this merger weren't easy, either. But they were collegial throughout, marked by a strong commitment to good faith negotiating on all sides. The JOLT members - all colleagues in the association profession - were able to find common ground and work together effectively.

Although the merger had financial implications – organizational assets were being transferred, future revenue potential was being affected, etc. – no cash was exchanged as part of the merger. Although JOLT members held to their fiduciary responsibilities for their respective organizations, they reached a consensus not to let financial metrics control or drive the negotiations to achieve a better future.

At several junctures, JOLT leaders commented on how hard the negotiating teams worked – spending hours in what were sometimes two-day meetings – to decide tough questions before critical deadlines in the process.

Developing the overall concept and framework for the merger – announced in January 2004 following several months of discussion – turned out to be the easy part. The boards of all four organizations approved the broad parameters of the agreement following a briefing by JOLT.

Then the real work began as JOLT and the staff teams conducted due diligence and delved into the details of how the merger would work.

“We all had fiduciary responsibilities to our organizations,” one leader remarked, “and sometimes these were in conflict as we went through this. We sometimes thought about what we might be losing, but we always shifted our thinking to focus on what we could gain.”

JOLT members centered their discussions around the needs of the component organizations and were able to craft a solution that responded to those needs.

“One element of success in the negotiation was that great flexibility around the understanding of needs, along with creative ideas, which enabled solutions to develop,” said Dave Ryder, the 2003-04 chairman of The Center for Association Leadership.

"For me, what kept this in focus was our need to do what was best for our respective members and customers," remarked Richard B. Green, chairman of the ASAE Foundation and vice president, association sales & industry relations for Marriott International. “It was clear there was overlap and competition between the organizations and it wasn't healthy competition – it was just diminishing our resources. The member or future member is the one who would benefit from unifying these groups and creating a single organization that would operate from a position of strength, leverage future-focused strategic research, and a provide proven cutting-edge learning programs.”

While the big picture view provided useful context for negotiations, many structural details were worked out in the discussions.

“The toughest point in the process was after the announcement was made public and we went back and got into the details, dealing with issues such as governance, culture, and how the organizations could be ‘independent and interdependent,’” Kuhn said. “But we continued to say that the bigger goal was more important than any of the details, and that's what got us through. Stakeholder input was tremendously important – it made us go back to the drawing board on some things. It was during that time we developed the joint committee structure between the ASAE and Center boards for nominating, planning, and audit/finance. We also decided that the new volunteer leaders who would lead the organizations following the merger would answer many of the questions and make it work.”

Peter Moran, the 2003-04 secretary-treasurer of GWSAE and executive vice president & CEO of the Society of American Florists, noted, “What impressed me during the negotiations was that whenever we seemed to get to an impasse, we would always come back to the original goals we identified before the process began. That seemed to get us on track. Also, Tom Kuhn always reminded us that we have to trust that the people who would follow us in leadership roles will make the right decisions for the time under the new structure. This was a guiding light in my mind.”

Egos and personal agendas were notably absent throughout the negotiations. “Never did I see anybody on either side of the table say, ‘What is going to happen to me or my position?,’” Nappi observed. “Their comments were always unselfish, focused first and foremost on what is best for the profession and then what was best for the organizations involved. That's what kept me engaged.”

Another key factor in the success of the negotiations was that most of the board members of the four organizations had also served as volunteer leaders in the other organizations. This cross-pollination made it easier for everyone to see the situation from more than one perspective.

“We all had major stakes in both ASAE and The Center,” Kuhn remarked. “In addition to my leadership role at ASAE, I had been a contributor to the Center and believed in Susan Sarfati's leadership of that organization. I also served on the search committee that brought John Graham aboard.”

“There was an inherent level of trust among the players and a shared history among a lot of the players,” Nappi commented.

Moran added, “I never felt that there was a hidden agenda among the JOLT members. I think we had differing opinions based upon the organizations we were representing, but there were no private agendas.”

Inspiration and encouragement came from key people in the process and from many places.

Moran praised the leadership of Kuhn and Balestrero, the respective chairmen of ASAE and GWSAE: “I don't think this could have happened without their leadership. They were absolutely the right people at the right time to lead us through this process.” He was also energized by the enthusiasm of Graham and Sarfati, the staff CEOs of ASAE and GWSAE. His views were echoed by many JOLT members, who realized that the ultimate success of the merger would depend on their ability and willingness to make it work at the staff level.

JOLT members representing the GWSAE and Center also appreciated the role that their fellow board members played in the process. “They kept us focused on the right things,” Nappi recalled, noting that when negotiators are deep in the middle of a process it is sometimes hard to maintain a broad perspective on a situation.

After emerging from one negotiating session, Greg Balestrero, chairman of GWSAE, gained inspiration from a quote on the side of the National Archives building that he said helped put it all in perspective. “All of the past is prologue,” the engraved letters read. “This struck me as profound,” he observed. “Legacy can be the foundation for the future or the anchor to hold us back. We believe this merger is a prelude to a strong future.”

Through the process, JOLT members were also mindful of the importance of acting quickly to take advantage of the enthusiasm and commitment of the group.

“I truly believe what kept everyone going was we all believed we had an opportunity to make something very positive happen for the entire association community but we had a very small window of opportunity to act,” Moran said. “Dave Ryder, having been through many mergers, always reminded us that time is the enemy of any merger. It is best to move through the process as quickly as possible as long as the due diligence is conducted. If the process takes too long, then the positive energy begins to change directions.”

“We did what we had to do to get this done, and that's what I am proud of,” Nappi said. “This is my proudest association moment to date, and I am extremely proud that there were no personal agendas in the process.” He added, however, that “this is only the first chapter. We did the right things for the right reasons, but let's give it three years and see how effective it is. This is a journey, not the destination. I'm betting that three or four years from now it will be bigger and better than even the most optimistic projections. It couldn't have been that way if we had overstructured it – there had to be a certain amount of ambiguity and freedom for future leaders to shape the organizations.”

Finally, the negotiations needed to be based on a presumption of success - there were never any “Plan B” scenarios developed. “There couldn't be a bailout provision or a potential for divorce,” Nappi declared. “Divorce was not considered an option in our planning. This kept us focused on making it work.”

Culture Issues

The difficulty of combining different cultures is often cited as the biggest reason why mergers fail.

One JOLT member reported that he spoke with other colleagues who tried mergers and failed, and was told by each of them that culture was the reason. Numerous books and articles cite culture as a critical element of successful mergers.

Consequently, it wasn’t surprising when cultural differences were quickly highlighted by members and stakeholders as a key issue in this merger after the concept was first announced. Comments poured in via e-mail, telephone, in Town Hall meetings, and in conversations. A sampling:

“I hope that ASAE-GWSAE are considering the cultural aspects of this merger.  In fact, the research says that most mergers and acquisitions fail because of the cultural differences of the two organizations. From my perspective, you have ASAE which is more staid and conservative and dominated by a handful of execs and GWSAE which is more flexible and innovative.”

“My greatest concern is that the ‘openness’ of GWSAE might be lost. It is tremendously easy to get involved in GWSAE in any way you want, including serving on a council, no matter what level you are at professionally and no matter how long you’ve been a member.”

“The hallmark of GWSAE is how easy it is to get involved. We want that to remain the same.”

“I am concerned that the efforts of the rather regionally directed GWSAE will be swallowed up by the national ASAE.”

“It is my observation that the cultures of ASAE and GWSAE are significantly different. These cultural differences are clearly seen in approaches to customer service and in the methods used for leadership/professional development and organizational growth through progressive education programs.”

As these types of comments poured in, JOLT members and staff leaders insisted that cultural differences would be resolved and that the new culture would satisfy concerns.

At one point in the JOLT discussions on this topic, ASAE Chairman Barbara Belmont, CAE, declared, “I don’t know why we are talking about different cultures – we should be talking about how we can take the best of all four organizations and create a new culture.” GWSAE Chairman Greg Balestrero recalls that this comment was a turning point for him – it changed how he thought about the culture question and how it could be resolved.

Sarfati repeatedly emphasized in public comments that they “heard the message loud and clear” about preserving the GWSAE culture, and pledged to ensure that the customer service and friendly interaction that defined the culture would continue.

“The next couple years will determine the culture,” Balestrero noted. “The transition board of The Center is comprised 50 percent from the GWSAE community and 50 percent from the ASAE Foundation community. If we go into this with the commitment that we will come out with a culture that has the best of both, it will work. It needs to be a great place to volunteer your time, and it has to start with the volunteer leaders.”

Member and Stakeholder Feedback

If immediate positive feedback is a sign that a proposal is on the right track, then it shouldn’t be a surprise that the merger was approved.

The communications strategy included a series of e-mails to members of ASAE, GWSAE, and all stakeholders involved in the four organizations. On January 16, 2004 – the day after the four boards approved the merger concept – two e-mail messages were sent. The first went to all members and stakeholders, including GWSAE members. The second went only to GWSAE members.

Each e-mail provided a link at the bottom for recipients to click to provide comments directly back to Graham and Sarfati. This mechanism helped generate a tremendous amount of feedback – many of which were received within minutes or hours following release of the e-mail.

What Members and Stakeholders Said

Members and stakeholders of all the organizations involved were quite thoughtful in their responses, offering a wide range of views and opinions that provided a rare window of insight into how members were thinking.

In response to the initial e-mail to all stakeholders, 82 percent of the responses were positive with no questions asked – a truly remarkable result considering the magnitude of the proposed merger.

Many respondents also appreciated the style and content of the e-mail communication. They liked receiving a prompt update delivered to them personally and especially appreciated being asked for input, which of course they offered. Some of the positive comments from association professionals located both in Washington, DC, and around the nation included:

“You have my compliments and full support in the consolidation. I believe it will elevate our profession, recognition and influence to heights previously only dreamed of.”

“Great idea. This is real progress. Congratulations on doing what is truly best for the association community.”

“It is about time. This is the best thing to happen to our association community here in Washington. Best of luck – you have my support.”

“I personally think this is a great idea and an enhancement to my membership.”

“A long overdue decision. It only makes sense. Good work and good luck!”

“Outstanding move. This will create much better value for all.”

“You are both to be congratulated. It strengthens the leadership team and provides a seamless environment for members.”

“WOW! A brave new world for associations! Congratulations to all who participated in this monumental undertaking. You give new meaning to risk-taking and creative thinking. But, most importantly, the leaders of the four pillar organizations have boldly ‘walked the talk.’ I’m on board!”

“Congratulations to you both. This makes all the sense in the world.”

“Bravo!!!!!!!!!!!!!!!!!!!!!!

Great Consolidation!!!!!!!!!!!!!!!!!

A big win for the association management profession!!!!!!!!!!!!!!!!!!!!!!

Don’t let anything get in the way!!!!!!!!!!!!!!!!!!!!!!!!!!!”

“May I congratulate both of you on your bold move, courage, mutual trust, and vision to advance the profession. I know this could not have been easy.”

“I am astonished and delighted with this development. . . .For the first time I note a cooperation between both organizations rather than competition. I commend everyone on the JOLT team. . . .Education is a must for all of us in this fast-changing world. What you know today will not be enough tomorrow and all of us must continue to learn. This consolidation will give us one voice to learn all that is being offered and one place to receive this education. . . .As a past member of the Board of both ASAE and GWSAE, I could not be happier or more impressed.”

“I commend you for this extraordinary display of leadership. As a former member of the ASAE Board and Executive Committee (and a 30-year plus member of ASAE), this is the most dramatic and positive development in the history of the organization and the association management community.”

“As a former member of both ASAE and GWSAE as well as former staff member of the ASAE Foundation, I applaud this merger. It has been discussed (even if in whispers) for years that these two organizations frequently compete for members and member participation.”

“As a former chair of the ASAE Small Associations Advisory Committee, I support the move to consolidation. . . .I would hope that a merger as contemplated would possibly cause ASAE to focus more strongly on the smaller associations and on the majority of state affiliates.”

“This is a terrific idea. It brings more talent to every opportunity and eliminates wasteful overlap and competition. You have my full support. Just one concern. As a member out here in the hinterlands (Chicago), I know both of you will want to put special emphasis on the commitment of the combined entity to provide leadership and programming outside the DC area. You have a lot enthusiastic members outside of DC, and I know they will be looking for reassurance that the consolidation will not lead to a lessening of attention and focus on them.”

“It’s a great idea. This puts a capital ‘S’ on the word strategic. It gives focus and avoids duplication. It capitalizes on the strength of each organization. What took you so long? Encore to all of you for having vision! Purpose prevails.”

“What a superb initiative. While working out all the issues will not be easy, I am confident, in the end, that the collective memberships, our profession and organizations we all serve will be greatly enriched by what you are working to achieve. Excellent!”

“I think this is a wonderful and logical idea! In this day and age, the sharing and merging of resources makes more sense than ever.”

“A very wise a prudent idea. Combining these entities will strengthen their ability to serve members and the association community. The existence of several entities just confuses the association community and it often looks like these entities are in competition with one another for no good purpose.”

“In today’s environment, I believe that this is a very futuristic and proactive move to ensure not only the survival of the associations, but the growth of them, especially as the role models that they must continue to be for the rest of our industry.”

“I’m proud when organizations can put ego and power aside in a collaborative effort to maximally serve their constituencies. It’s what we associations have to do all the time.”

“Let me commend you on doing something so many other successful organizations fear: looking outside of your own walls to do something that potentially would benefit the members, which is why these organizations exist in the first place!”

As expected, many stakeholders also had questions and concerns. Some of these comments included:

“My initial reaction is VERY negative. This will further entrench the impression that ASAE is a Beltway organization. Only one person on JOLT is from outside the Greater Washington, DC area. DC execs will have even more influence in the new organization. Evidence of this is the location of the two informational meetings in the DC area. Why not an outreach effort to the rest of the membership?”

“. . .My future participation will depend on how you shape the new organizations. On the one hand, you could become more DC-centric, in which case you will probably lose many of us from the rest of the country. On the other hand, the efficiencies gained through the merger could free up resources and help you focus on providing additional value to the rest of the country. I will be following which option you choose with great interest.”

“My major concern, as one of the minority who resides outside the Beltway, is that a merger with GWSAE will be mainly a boon to those located in the Washington area. Please don’t forget about the ASAE members who are carrying out association work elsewhere. As it is, a number of ASAE’s educational and networking activities are out of bounds for us.”

“A concern: Will ASAE be disproportionately influenced by GWSAE because of the geographic proximity? I can understand and respect the financial imperatives behind this decision. However, as a local association I already feel the magazine has too much vendor content. This dilutes a major benefit of membership. Couple that with unintentional undue influence by a convenient source of member attitude sampling – Washington area associations – and you could suffer from ABS. . .Acquired Beltway Syndrome.”

“Consolidation is the way to go. I only hope that non-Washington associations, particularly those in the western United States, will get some expanded education offerings.”

“It appears as though, to be a really involved member, one would have to be resident in the Washington, DC area in order to get the most benefit from membership. That is already an issue (and one being dealt with by virtue of this proposal). It does not, however, address how ASAE will be addressing the issues of ALL its association members.”

A series of Town Hall meetings across the country provided opportunities for these individuals and other stakeholders to express their opinions to Graham and Sarfati in person and ask questions about the proposal. These views, as well as those regarding the culture of the organizations, played a major role in helping to shape the final merger proposal.

Praise and Encouragement from the “Merger Community”

Some interesting responses came from executives who have guided their own associations through mergers, are in the process of doing so, or are considering this. They commended JOLT and the four organizations for putting egos aside and having the courage to tackle change that was driven by market forces. They all know how hard it is, yet they believe the end result is worth the journey. Some comments included:

“As a member of both ASAE and GWSAE, and the CEO of a recently merged association, I fully support the consolidation plan. Thank you for your visionary leadership. I know this process will not be easy, and I appreciate your hard work to make it happen. Please know that at the end of the day you will have created a unique institution that will be of great value to our community.”

“I am the managing director of [an association] which represents 7,000 independent [business owners] across the country and Canada. [It] is a division of a 100-year-old organization of distributors in [our] industry. We are in the midst of merging with another association into one corporate entity with different sections for membership. The 36-month-long process has had its ups and downs and with a 20-member staff, we are anxious for its completion. We have had steering committees and bylaw committees. We have had confusion and frustration. We have members who are angry, reluctant, sad, and vulnerable. We have had tears of excitement and fits of anger. Mostly over change. People have such a hard time accepting marketplace changes, business and revenue models changing, and just plain common sense. I want to applaud you for reaching out to me as a member and asking me for my thoughts and voice. I feel connected to your journey. I believe if the JOLT committee is recommending this consolidation, then I will be supportive as I trust that people closer to the discussions are doing the right thing, for the right reasons and are putting aside their differences through courageous conversations. I hope you find support and clarity during this adventure. I hope you gain insight and knowledge and I hope that when it is behind us all and we all have one organization, that you are proud of your vision and dedication.”

“Our association, one of over 14 that claim to speak for laboratories in this country, have been trying to achieve such an arrangement and every association that we approach looks at us as if we are from outer space. Now, with the joining of two such prestigious organizations, led by two of the most admired association execs, we have a model to use as an example. What you have done is what many associations will need to do in the coming years – or perish.”

“I believe consolidation is in the best interest of all the organizations. We may be undergoing the same exercise ourselves in the future, so I fully understand the dynamics of the experience which you are all about to undertake.”

“Five years ago I was involved in a consolidation of four associations into [one association]. Our experience has been very positive. The membership has indeed benefited from the consolidation and the synergies expected have been realized.”

“It makes sense. Associations are a reflection of the industry or profession they represent, and for the past 10 years mergers of all kinds and shapes have taken place in the non-association market. My own association is the product of mergers with two other associations, one in 1991 and one in 1998. Members now pay dues to one organization rather than three, and that is what they wanted.”

“Since mergers and consolidations aren’t new to my membership, I’m not surprised by your actions. Taking the honorable steps towards saving the organizations so that persons such as myself may continue to realize the many high-quality benefits I’ve become accustomed to, is admirable. Your hard work is appreciated. Possibly in the future you could have an educational program or an article outlining how it all came together and the agreements between the organizations. This could serve as a model for those associations that are considering consolidation with other associations.”

“In 1996-97, I chaired the Michigan Society of Association Executives and its merger of three organizations representing the profession in Michigan. It was hard work and required an open mind with respect to looking beyond vested interests and the significant histories and politics of those associations. We phased the merger in over a three-year period, allowing the several entities a reasonable time to make it work. It did work and I believe the current programs in Michigan reflect this.”

“[Our association] is a product of two associations with history dating back to 1932 that merged together in 1975 to form one association. The boards of the two associations realized that they were supporting the same industry with the same members and programs. They became a lot stronger and were able to provide more services and programs to their members once they joined forces.”

“We face this very same issue, in that so many specialized associations have branched off from ours that it is becoming impossible for anyone to adequately participate in more than one or two, let alone all of them. I think this is the wave of the future and is the only way to survive. I applaud the various organizations’ leaders’ willingness to move beyond any ethnocentric feelings and face reality in order to create a viable future.”

“Industry Partner” Considerations

Most associations are heavily dependent on support from their supplier communities – companies that sell products and services to their primary members. The associations involved in the merger commonly refer to these suppliers as “Industry Partners.”

The four organizations involved in this merger were no exception. Revenue from exhibits, advertising, sponsorships, contributions to capital campaigns, supplier dues, and other sources was essential to fund association and foundation programs.

The economic downturn experienced by the association community in late 2001 and beyond illustrated just how important this revenue is to these organizations. Faced with drops in advertising revenue and other Industry Partner support, coupled with a drop in overall participation from association members, ASAE and GWSAE were both forced to made significant budget cuts. ASAE also laid off many staff. Both organizations handled the economic downturn and emerged with financially healthy operations by FY 2004, when merger discussions began.

A key concern upon approval of the merger concept was that Industry Partner support would drop sharply on speculation that certain programs such as magazines or trade shows would be eliminated. From the beginning, special e-mail communications were crafted for Industry Partners, providing information and updates on each major program that relied on their support. This information was also featured in the “Frequently Asked Questions” section of the Better Together Web site.

For example, ASAE published a monthly Association Management magazine, and GWSAE published a monthly Executive Update magazine, both reaching large segments of the association community. While each had a distinct style and approach, they clearly had some overlap in the market. Industry Partners and other stakeholders were told that both magazines would continue to be published until at least July 2005 – one year into the merger. They were also told that the future of the magazines after that date would be determined by a complete evaluation of the needs of readers and advertisers and development of a strategy. This succeeded in preventing any significant defections by advertisers.

Another major concern was Industry Partner support of Springtime™, a large one-day trade show held by GWSAE that generated a significant portion of this organization’s revenue. GWSAE was in the midst of selling booths for the show, which was scheduled for May 2004 – before any final decision would be made on the merger. Industry Partners were assured that Springtime would continue as a major trade show in future years regardless of the outcome of the merger – GWSAE made clear that since it was such a popular event it would surely continue. Springtime proceeded to break all previous records for booth sales and attendance in May 2004.

At the time the final merger announcement was made in late June 2004, no programs had suffered a significant decline in Industry Partner support.

Due Diligence

The merger process included detailed legal and financial due diligence performed on behalf of the four organizations. Due diligence reports on the Center for Association Leadership and GWSAE were prepared by the law firm Shaw Pittman and the accounting firm Tate & Tryon on behalf of the ASAE and the ASAE Foundation, and presented to the ASAE Board of Directors and the ASAE Foundation Board of Directors on April 1 and April 6, 2004, respectively.

Due diligence reports on the American Society of Association Executives and the ASAE Foundation were prepared by the law firm Venable, LLP and the accounting firm Langan and Associates on behalf of GWSAE and the Center, and presented to the GWSAE Board of Directors and the Center Board of Trustees April 23-24, 2004.

Many areas were examined in these reports, including financial statements, contracts, insurance coverage, tax liabilities, real estate investments, employee benefit plans, and others.

An important part of due diligence was also conducted by staff, as they met with their counterparts at the other organizations involved and worked together to develop proposed budgets and programs of work that would be possible under the merger.

Staff Integration

From the beginning, each of the organizations involved recognized that effective staff integration and full communication about the process as it unfolded would be essential for the merger to succeed.

Key senior staff members from all four organizations were involved early in the process – helping to prepare the initial merger concept proposal for the four boards of directors. Once the merger concept was approved and announced, volunteer leaders and CEOs immediately held separate meetings with the staffs of the organizations to brief them. These initial meetings focused on the positive aspects of the proposed merger and the future potential to serve the association profession in a better way. This was an important first step in keeping the entire staff informed about the process as it unfolded.

Within two weeks after the merger concept approval announcement, the senior staffs of all four organizations met for a full day to begin discussing how they would share information and work together in the due diligence process that lay ahead. They recognized from the outset that the bulk of the due diligence work would fall on them as they prepared information for JOLT and the four boards to review. The group included about 16 people, and was dubbed the Staff Integration Steering Committee (ISC).

Center for Association Leadership Chief Operating Officer Scott Steen and ASAE Foundation Executive Director Sarah Varner were named co-chairs of the ISC. The collaborative working relationship immediately established by members of the ISC helped them develop the following purpose and guiding principles for their work together:

Purpose of the ISC

"To create a vision and a plan for moving forward together to better serve the association community."

- Map out Integration of ASAE/Center functions consistent with conceptual model

- Identify programs, opportunities and challenges in assigned areas and propose solutions

- Identify gray areas and propose alternatives

- Help to create a new culture for the new organizations

Guiding Principle

- View the new world as if the old didn't exist

- Act as a single, unified team

- Participate with honesty and integrity

- Focus on what is in the best interest of the association community.

- Consider the ideal situation first without resource constraints.

- Reach out to others to get the best minds involved.

The ISC Process

Ten subcommittees were established to create a "statement of purpose/charge" for each area that would define their focus of work. The subcommittee areas included:

- Communications

- Education

- Finance/Legal

- Human Resources

- Meetings

- Publications

- Member Services

- Sponsorships

- Technology

- Volunteers

The subcommittees began meeting on their own schedules and reporting results back to the overall ISC approximately every two weeks. While significant progress was made, it was apparent after a few weeks that an in-depth staff retreat was required to develop a consensus on the overall goals and direction for the merged organizations to lay a foundation for developing specific structures and work plans for each area of the organization.

This retreat was held over a weekend in mid-March and was designed to explore several issues, including the strengths and cultures of the four organizations, staff hopes and goals for the merger, and the specific roles the new Center and ASAE would play if the merger was approved.

As the retreat progressed, the staffs of all four organizations found that they shared a common vision for the values and culture they sought to create. The group found many of these values articulated in The Center for Association Leadership strategic plan, which was developed in the months preceding the merger.

The retreat was also an occasion for personal and professional bonding among the senior staff. They told stories about their shared experiences with the organizations involved, including the positives and negatives. They also described their dreams, and their fears, about what the merged organizations would be. Time for a few social activities helped build camaraderie.

Key outcomes of the retreat included drafts of the following: a core purpose, description of the brand promise, enablers, workplace values, roles and relationships for the two organizations, and potential goals and strategies. This work provided a substantial underpinning for the work of the ISC.

The conclusions of the retreat were that ASAE and The Center should be:

- The principal resources for ideas, models and learning that advance associations, association professionals, and association Industry Partners.

- A warm, vibrant, and welcoming community of professionals that inspires those who interact with us to become actively engaged.

- The recognized leader in advancing, promoting and supporting the value of voluntary organizations worldwide.

- The leading model of organizational excellence and execution within the association profession.

As the ISC achieved conceptual agreement on the key functions of ASAE and The Center following the merger, staff also recognized the extensive overlap in some key areas. Out of this realization, the ISC developed the concept of “Shared Services,” which would create several departments that would service both organizations in the areas of human resources, finance and administration, information technology, marketing, public relations and communications, meetings and expositions, strategy, and market research.

Because of the success of this retreat and its importance in defining the “big picture,” staff agreed that this should have done at the very beginning of the process after the merger concept had been announced. Nevertheless, it succeeded in creating the framework needed to define the essence of what the merged organizations would look like, which became an integral part of the final presentations to the four boards, GWSAE members (who were required to vote on the proposal), and the entire member/stakeholder community).

By mid-April, the ISC subcommittees completed Business Area Plans for each of the 10 operational areas, which served as a basis for creating an overall proposed workplan and budget for the merged organizations.

One area that proved challenging to plan before the merger was finalized was education – the very core of what the merger was designed to address. Because of the lead times required for booking hotel space and promoting events, ASAE and The Center were forced to make commitments on some programs before the merger was approved. If the merger had failed, these programs would have still been conducted on a joint basis.

Overall Staff Role

Throughout the process, care was taken to inform the entire staffs of the four organizations about how the due diligence was proceeding, including opportunities for them to ask questions and voice concerns. Several formal and informal meetings were held, including a few joint social activities. On the day of the board votes on the final merger proposal, the entire staffs of the four organizations were invited to a large joint meeting/social event immediately following the vote to hear the results.

Ongoing Staff Integration

Graham and others noted many times during the process that the merger would not be complete on Day One following formal approval – it would take months and even years for all facets of the organizations to achieve full integration. Staff would bear primary responsibility for implementing change as directed by the boards of the two organizations.

Speaking only three months after the merger took effect, Kuhn observed, “The most delightful thing I am seeing so far is that the entire staff is working together so well. This happened very quickly – usually it takes a long time to achieve that.”

GWSAE Member Vote Campaign

The most challenging aspect of the merger was handling the dissolution of GWSAE, a 76-year-old organization that had achieved its highest level of success in the years leading up to the merger. GWSAE members and stakeholders continually raised the issue of retaining the “GWSAE Culture,” defined as an open, welcoming, and customer-focused culture that stimulated innovation and creative thinking in an environment that people liked.

No one wanted that culture to disappear, yet the merger proposal called for GWSAE to cease as a separately incorporated organization. Under the proposal, the programs, services, and assets of GWSAE would be transferred into The Center for Association Leadership, where they would continue to be offered through an entity called the “GWSAE Network.” Since The Center was already a subsidiary of GWSAE, and in fact already offered all the education programs that GWSAE members attended, the proposal offered significant continuity in this area. The Center staff also consisted of essentially the same individuals who provided GWSAE services. GWSAE members also stood to benefit by no longer paying dues to two organizations, GWSAE and ASAE – they would automatically be part of the GWSAE Network by virtue of paying ASAE dues.

Everyone involved in the merger realized that the GWSAE member vote would be the most important phase of the process. No matter what the boards of the four organizations decided, it could all be nullified by a negative vote by GWSAE voting members (consisting of association professionals members).

The vote was required to dissolve GWSAE and transfer its assets transferred into The Center. ASAE members were not required to vote, since their organization was not changing in any significant structural way. The Center and the ASAE Foundation did not have members, so only board votes were required for those organizations.

GWSAE took great care to gather input from GWSAE members throughout the due diligence process, including four GWSAE Member Town Hall Meetings (held in each major area of the Washington, DC region), e-mail communications from GWSAE President & CEO Susan Sarfati, and other outreach programs.

Sarfati continually reinforced the GWSAE member voting process as essential in approving the merger, saying on several occasions, “If the members don’t want the merger, it can’t happen,” She trusted them to make the best decision.

Many GWSAE members and stakeholders voiced their opinions about the culture in no uncertain terms. Many drew a sharp contrast between the culture of GWSAE and ASAE and feared that the larger national organization (ASAE) would subsume the GWSAE culture.

Since the culture of The Center (as a subsidiary of GWSAE) was largely the same as GWSAE, the final merger proposal included a provision to house the GWSAE Network in The Center for at least two years.

Following board approval of the merger in late May, GWSAE provided 30 days’ notice to members of a special member vote to dissolve the organization and transfer its assets to The Center. This notice was required by GWSAE bylaws.

GWSAE then developed a “Get Out the Vote” campaign, designed to provide members with the maximum opportunity to learn about the merger and cast their vote. Campaign elements included:

- Three member briefings to share information and allow members to answer questions

- Series of e-mail reminders about voting

- Complete packet of information providing background on the merger and voting instructions

- Telemarketing campaign by board members and staff to all GWSAE voting members, offering an opportunity for them to ask questions and encouraging them to vote

- Postcard reminder mailing about voting

The campaign was a team effort involving volunteer leaders and staff. At the board meeting where they approved the merger, GWSAE Board members emphasized their willingness to help with this effort, which they did through the telephone campaign.

Recognizing that many voting members would not be able to attend the member vote meeting, GWSAE established an absentee voting process that allowed members to vote at any time up to one day before the voting member meeting.

To ensure the integrity of the voting process, GWSAE hired Survey and Ballot Systems, Inc., an independent election services firm based in Eden Prairie, Minnesota, to administer and tabulate the ballots.

About two weeks before the member vote meeting, one longtime GWSAE member who opposed the merger sent a e-mail entitled “Vote NO on GWSAE Merger” to all GWSAE voting members that contained a four-page letter explaining why members should vote against the proposal. This came only a few days after members had received their voting information and had begun requesting absentee ballots and casting their votes. A version of this letter was also published in USAE newspaper. Balestrero and Sarfati responded the next day with an e-mail entitled “GWSAE Merger Questions Answered,” explaining that the previous e-mail was not endorsed by GWSAE, answering questions raised by the e-mail, and encouraging members to vote. ASAE Chairman-Elect Tom Kuhn also responded with a letter to the editor in USAE refuting several points in the member letter and stating his support for the merger.

In the end, GWSAE members provided a strong mandate for the merger. To earn approval, two-thirds of the GWSAE voting members who cast votes had to approve the proposal. Of approximately 1,650 members eligible to vote, 733 members voted either in person or by absentee ballot. Of those who voted, 78 percent voted in favor of the proposal, easily exceeding the required two-thirds majority.

Key Factors in the Positive Member Vote

In summary, the following factors helped achieve a positive vote for the merger by GWSAE members:

- GWSAE had already undergone significant change in 2001 when The Center for Association Leadership was launched. The success of this entity, and the ability of the Center to seamlessly deliver the same culture as GWSAE, was a good example of how a positive culture could endure in the midst of change.

- GWSAE members trusted GWSAE President & CEO Susan Sarfati, CAE, implicitly. She spoke many times about how the organizations “heard the message loud and clear” about preserving the culture, and her promise to keep the culture was readily accepted by many members. Sarfati earned this trust over a ten-year period of leading GWSAE, continually introducing new programs and building the culture that members liked.

- GWSAE members were given ample opportunity to voice their concerns and ask questions at Town Hall Meetings, member briefings, and the GWSAE vote meeting itself. Sarfati and ASAE President & CEO John H. Graham IV, CAE, also invited direct feedback via e-mail and telephone, along with a commitment to respond to questions and concerns.

- A commitment was made to continue many of the programs, benefits, and services of GWSAE in a new entity called the GWSAE Network, to be housed for at least two years within The Center. This allowed the same staff that supported the GWSAE culture to continue to be involved in providing services to former GWSAE members and stakeholders, allaying their concerns.

One GWSAE Board member who thought long and hard about the merger captured the views of some people by saying, “I had a lot of ambivalence but I feel very good today (the day he voted in favor of the merger as a Board member). I really believe that the combination can be bigger and better than the sum of its parts. There is a lot of angst locally about doing away with GWSAE. People need to know there is still a home for them.”

Communications

JOLT recognized from the beginning that effective communications throughout the process would be essential for the proposed merger to succeed. To develop a communications plan and handle the communications program, the organizations hired Association Vision, a communications firm led by Al Rickard, CAE, who had previously worked at both GWSAE and ASAE, and who had also been editor of one of the industry trade publications.

A full communications plan in place before the January 15 announcement of the board approval of the merger concept. Plan objectives included:

- Clearly communicate how the proposed consolidation will add overall value to what the four participating organizations now offer.

- Reinforce and enhance existing brand loyalties to the four organizations, including setting the stage for establishing brand loyalties to new organizations where necessary.

- Frame the discussion in a positive, future-oriented way and effectively answer questions and concerns from stakeholders.

- Ensure that the overall perception of the proposed consolidation is a positive one that will preserve existing membership participation and Industry Partner financial support.

Several key audiences were identified, including:

- Board Members and other volunteer leaders (such as committees) of the four proposed consolidation partner organizations

- ASAE Members

- GWSAE Members

- Center Circle Club Members (Associations)

- Employees of the four organizations

- Industry Partners

- Allied Society Leaders and Members

- Trade Press

- Policymakers/Government Officials

From the beginning, the goal was to provide as much information as possible to all audiences and continue to provide periodic updates throughout the process. A series of e-mail messages sent to all stakeholders under the joint signatures of Graham and Sarfati provided several important updates. Many members praised this process, saying they appreciated the updates and felt as though they were well-informed as the merger proposal was considered.

To focus the messages and information provided to the media, Graham and Sarfati served as the only official spokespersons. All volunteer members, staff, and consultants involved in the merger discussions signed a confidentiality agreement to prevent leaks of confidential information.

A Web site, entitled “Better Together,” was created immediately after the merger concept approval announcement, including e-mails to members and stakeholders, press releases, frequently-asked questions, and other information. A link to the site was provided from the home pages of each of four organizations.

The communications effort included a series of Town Hall meetings across the nation, where members and stakeholders could offer input and ask questions about the proposed merger. These events reinforced the goal of gathering input to help shape the final merger proposal.

While the initial approval of the merger concept in January 2004 made it appear to some stakeholders that the merger was somehow a “done deal,” the process of gathering stakeholder input through the Town Hall meetings helped demonstrate that this was not the case. The feedback gathered through these meetings, plus responses to e-mail messages, phone calls, and informal conversations with stakeholders shaped the final merger proposal in significant ways. For example, GWSAE members delivered the message loud and clear that they wanted to retain the best features of their organization, which contributed to the structure and program offerings of the GWSAE Network, the entity within the merged organizations designed to serve their needs.

Many ASAE members spoke of the need to expand education program offerings across the nation, which helped influence the scope of programs developed in this area for the first year under the merged organizations.

Press Coverage

The association and meetings industry trade press took a strong interest in the proposed merger, and the regional business press also covered it. A wide range of publications and Web newsletters covered the merger as it unfolded, including the following publications:

Association Management

Association News

Association Trends

Convene

ConventionPlanit.com

Executive Update

Expo Web

Meetings & Conventions

Meetings East

Meetings Focus

MeetingsNet

Meeting News

Meetings South

Meetings West

Mid-Atlantic Events

Minneapolis-St. Paul Business Journal

NonProfit Times

Successful Meetings

Tradeshow Blues

Trade Show Executive

USAE

Washington Business Journal

Association Forum, an ASAE “allied society” in the Chicago area, received many comments about the merger in its online “blog,” providing an opportunity for many stakeholders to voice their opinions publicly. Views were expressed on both sides of the issue.

JOLT held an initial press conference immediately following approval of the merger concept by the four boards on January 15, 2004. The media viewed a presentation that was shown to the four boards and received press releases and other background on the proposed merger.

Throughout the process, the trade press was invited to participate in all public meetings, and responses to media questions were provided as quickly as possible. Press releases were issued following Town Hall meetings to ensure that the media had full information about these events and the comments made by members and stakeholders.

Much of the trade press coverage was balanced and fair, especially at the beginning of the process. As the process unfolded, the media became a forum for spirited discussion about the merger. Comments from many members and stakeholders appeared in articles and letters to the editor. Some publications conducted unscientific “polls” of members to try to gauge potential voting trends.

Branding

As the due diligence process unfolded, it became apparent that an organized process to brand the new organizations if the merger was approved would be extremely important. To facilitate this, the organizations hired PCI Communications, a branding firm with previous experience in handling branding in mergers. PCI conducted audience research, branding development, strategic planning, and created presentations for the boards and key audiences.

Lessons from the Merger

Many valuable lessons can be learned from this merger. The process, while not perfect, produced a highly positive result. Among the 80 board members of the four organizations, all but one voted in favor of the merger. When it came time for the GWSAE member vote, 78 percent approved the merger. By any measure, this is a strong mandate for change.

But even if the merger hadn’t been approved, it could have been called a success on several levels.

On June 30, 2004, just minutes before the results of the GWSAE member vote were announced, GWSAE Chairman Greg Balestrero stood before a crowd of more than 100 members and called the proposed merger a success. It wasn’t because he knew the results of the upcoming vote – he didn’t – but because he recognized that the process leading up to the final vote was the real success.

“The journey is more important than the destination,” he declared. “Whenever you get members talking and debating about something for more than a year, it’s important.”

At this final member vote meeting, Balestrero recounted the history of discussions leading up to the merger and the reasons for proposing it.

His comments underscored how far the association community had come in recent years. For more than 20 years, volunteer leaders and staff of ASAE and GWSAE had talked about the potential for a closer relationship. At that moment, that goal had already been achieved.

A negative vote on the merger would simply have created a different model – less formal collaboration and partnerships would have replaced the defined structure of the merged organizations. One joint education program had already occurred before the merger vote (it was planned before the JOLT discussions were even underway) and several more were already in place for the coming year regardless of the merger vote.

Board members of the four organizations had met twice in joint meetings (once to approve the merger concept and a second time to approve the final merger) and found that they shared the same aspirations, dreams, values, and goals. Many of these board members had also previously served on the boards of the other organizations involved.

The same was true for the senior staff of the four organizations, who found they had much more in common than they had imagined. They met as a group numerous times and spent countless hours working with their counterparts developing specific programs of work as part of the due diligence process.

Eventually, these organizations seemed destined to merge – the only question was, “When?” It turned out that the answer to that question in 2004 was “Now.”

Key Lessons

No two mergers are the same, especially in the association arena. But many lessons emerged from this merger that could be applied to other association mergers:

Strategic Lessons

- Focus on the industry or profession, not the organizations. The impetus for this merger came from a group of leaders and staff setting aside organizational issues and focusing on what was best for the association profession. Once agreement was reached on that, the mission became clear and the best organizational structure to serve the profession was developed in relatively short order.

- Establish trust. Negotiations are built on trust, and a high level of trust among the players must exist for a merger to succeed.

- Be comfortable with ambiguity. It’s a natural tendency to try to deal with every potential scenario and possibility during merger negotiations, but it’s a nearly impossible task. Negotiators must be comfortable with some level of ambiguity, and trust that future leaders will deal with issues and challenges effectively.

- Leave egos at the door. No merger can succeed if egos are getting in the way. All negotiators and key executives must be comfortable with change not wedded to considerations driven by personal concerns. Otherwise, the process is doomed to failure. One of the main reasons this merger went through is that no one on JOLT or the senior staff tried to impose their ego on the process.

- Negotiate in good faith. All negotiations must be carried out with the intent to follow through and remain consistent on major items of discussion. It also helps to remain calm and collegial throughout, no matter how difficult the decisions become.

- Respect tradition. Even though tradition will be one of the casualties of any merger, it’s important to respect it. Consider the views of all members and stakeholders and craft the merger in a way that retains what’s positive. In this merger, the GWSAE brand and culture was critical to large numbers of members, so the GWSAE name was retained in a revamped “GWSAE Network” that had a different corporate structure but preserved what was important to members.

- Find the common cultural ground. After numerous members and stakeholders emphasized the cultural differences among the organizations, it would have been easy to dwell on these and make them a barrier to progress. Instead, volunteer leaders and staff focused on finding the positive cultural values they shared and built on them. The more they talked, the more they found agreement on broad values, goals, and the definition of customer service.

Tactical Lessons

- Seize the day! This merger began with immediate approval of the merger concept by the four boards. No information about the proposed merger was given out before that day. This preserved confidentiality and allowed board members to focus on approval of the concept without the process being tainted by public speculation in advance of the vote. Asking for approval of only the concept left Board members with plenty of room for further deliberation before being asked to approve the final merger.

- Set a reasonable timeframe for approval. Merger deliberations can last indefinitely if the process is not defined by a specific timeframe. Allow adequate time for gathering feedback and conducting due diligence, but keep it to a minimum. This forces all parties to focus on the critical issues and make a decision. Once the concept was developed and approved, this merger was completed in less than six months.

- Negotiate the major items first. Once negotiations begin in earnest, focus on the major items first when energy and commitment are highest and negotiators are not jaded by weeks of discussion. If any of these prove to be deal-breakers, it’s better to know right away before extensive resources are devoted to a potentially losing cause.

- Don’t assume anything. A natural tendency in merger negotiations is to avoid a tough discussion about a sensitive point, with the parties leaving the table with different assumptions. Avoid ambiguity at all costs, so unpleasant deal-breakers don’t emerge at the 11th hour. You can’t run what-if scenarios on everything, but for the major items it’s crucial.

- Engage a facilitator for difficult discussions. When faced with myriad issues involving a merger, it’s easy for a negotiating team or a board to veer off in many directions. Discussion can drift toward small issues while major items remain unresolved. Since the elected chairman and the staff CEO are actively engaged in these discussions, it’s hard for them to step back and refocus to stay on task. Hire a skilled outside facilitator and brief them on the major agenda items. Stick to the agenda to ensure results.

- Hire outside expertise as needed. We consulted with outside experts in mergers, governance, communications, and branding. The expertise of your lawyers and accountants are also critical.

- Don’t eat the elephant in one bite. The old riddle goes like this: “Question: How do you eat an elephant? Answer: One bite at a time.” This is especially true with mergers, which can be extremely complex. Even though the merger officially took effect on July 1, 2004, leaders repeatedly emphasized that the full execution of the merger would take months, even years. It isn’t possible – or desirable – to force a sea change of culture and operations on an organization overnight.

- Create mechanisms to facilitate the transition. Just as an entire merger cannot be implemented immediately, certain structural elements – such the final board makeup – cannot always be finalized right away. This merger provided for a two-year transition board that allowed key leaders from both organizations to participate in governance in the early years, with the final board structure to be finalized after two years.

Communication Lessons

- Explain why you’re merging. The impetus for a merger can be complex, and nearly everyone is conditioned to think that one or more of the merging organizations must be in financial distress. With this merger, all four organizations were financially sound, and the reasons for merging dealt with what was best for the profession – focusing organizational resources on the members and stakeholders, on better programs instead of competition, eliminating confusion in the marketplace, etc. But one of the most difficult parts of the process was convincing people that finances were not the driver.

- Identify the value proposition. The value proposition is only one step removed from explaining why organizations are merging. The value proposition must be stated in the language of the member or stakeholder – how will it benefit them specifically? In this merger, answers included lower dues, better programs, more benefits, programs closer to home, and focused market to reach customers, depending on the stakeholders.

- Communicate early and often with all stakeholders. Information about this merger was communicated rapidly with everyone, even in the absence of details about the process. Instead, the big-picture concept of what the merger could do for the profession dominated early communications. Later communications provided updates on the process as details were finalized. Accept the fact that some stakeholders will feel they received too much information, others will see the level of communication as just right, and others will feel they did not receive enough information.

- Speak with one voice. Determine at the outset who will speak for the organizations during the merger process. If this is two people, make sure they communicate regularly and say the same thing on all major issues. Any difference in statements, even subtle ones, will quickly be exploited by naysayers and the trade press.

- Provide information to the trade press. When a big story like a proposed merger breaks, the trade press immediately takes a strong interest. In addition to publishing information you provide, they will call board members, interview association members, conduct for/against polls, and speculate about the future. In the midst of negotiations and due diligence it is difficult to provide a steady stream of facts and information, but in the absence of information the press will search out news, which may not result in accurate or favorable coverage.

- Sell the final decision. Once a merger agreement is reached, sell it aggressively to members and stakeholders. Volunteer leaders and staff should be equally committed to the change – otherwise, why should members support it? They want to know that the merger is absolutely the right decision before supporting it with their vote (if required), membership dues, time, energy, and participation. In this merger, board members asked how they could help sell the decision to members who would cast the final vote, and a telemarketing campaign was launched that allowed them to communicate one-on-one with their peers.

- Provide ways to gather feedback. From the earliest communications, an easy mechanism was provided to gather input via e-mail (by replying to the initial e-mail messages), which quickly generated hundreds of comments. It allowed people to express their opinions and provided leaders with a good feel for the level of support for the concept. A series of Town Hall Meetings and other briefings provided more opportunities for stakeholders to ask questions and provide feedback in group settings both live and via audio conference.

- Be transparent. From the beginning, the organizations involved in this merger pledged a “transparent process” for all their communications. The process lived up to that, providing all the information possible without compromising ongoing negotiations and due diligence.

Staff Consideration Lessons

- Update and engage staff in the process. This merger was marked by the early and enthusiastic participation of both staff CEOs and their senior staff and regular updates to all staff. By engaging them in the process, the merger was actually driven by staff collaboration instead of being held back by staff fears of job insecurity and other issues.

- Be sensitive to staff. Any merger will create staff issues as positions are merged, eliminated, or restructured. This merger was easier than many because ASAE was understaffed at the time of the merger, eliminating the need for layoffs. However, not all staff will be happy with the changes, and it’s important to keep your team intact and morale high. Listen to their concerns and handle them as humanely as possible. If staff must be eliminated, do it quickly to avoid ongoing anxiety and provide generous severance packages.

Appendices

Appendix A: JOLT Member List

Appendix B: Merger Proposal Report and Recommendations