## Detailed
1. PUBLIC SAFETY: Protect the public through a combination of prevention, prosecution, correction and supervision
Objective #1: Ensure Deschutes County can meet its long term public safety needs
Department | Action | Measure | Target/Projection | Quarter 1 Update | Quarter 1 Comments | Quarter 2 Update | Quarter 2 Comments
Sheriff's Office | A. Maintain a safe and secure corrections facility | 1. Number of inmates released early due to matrixing | 0 | 0 |  | 0 | No forced early release
| B. Enhance public safety by installing the Alsea Geospatial Mapping System on all patrol vehicle mobile data terminals | 1. Number of vehicle traffic accidents in Deschutes County | Less than FY 2009 (152) | 137 |  | 169 in 2Q; 306 YTD | YTD accident rate is lower than same period last year. The procurement of the Geospatial Mapping System was started in Q2.
| C. Purchase and install the Veripic Digital Evidence System, hardware and software, to enhance evidence authenticity, storage and accessibility | 1. Installation of Veripic Digital Evidence System | System operational by Sept. 1, 2010 |  | Continued system evaluation with review of City of Bend PD's new system and RMS interface issues | On Schedule | Vendor quotes have been received. Continued due dilengence evaluation of vendor solutions.
Health Services | A. Increase local beds for mental health treatment, preventing more costly care or homelessness | 1. Number of new treatment beds by July 1, 2011 | 24 or more | 0 | Projects continue in development. First targeted opening for first quarter 2010. | 0 | RTH openings TBD. SRTF scheduled for Oct. 2010. Barbara's Place scheduled for July 2010
|  | 2. Number of total treatment beds | 64 or more | 40 | 40 is current bed capacity | 40 | 40 is current bed capacity
|  | 3. Percentage of community bed need (580) met by July 1, 2011 | 11% or greater | 7% |  | 7%
Administrative Services | A. Identify adequate funding for construction of jail expansion and maintain operations of work center | 1. Funding secured for jail construction | By June 30, 2010 | No Progress | Memo distributed to BOCC detailing ongoing problems with rezoning 216 acres in Redmond; Further discussion of issue scheduled for 2Q FY2010 |  | Staff is proposing $44 million bond measure for May 2010 election. Resolution for bond & creation of new debt service fund to be considered by BOCC in 3Q. Deposits from land sale can be deposited and used offset debt service payments from the bonds, if approved. If not approved, fund could pay for future bond sale.
Property & Facilities | A. Construct new Oregon State Police/911 building | 1. Complete construction of building | By June 30, 2010 | Construction began August 2009 | There were delays in building permits and additional requirements and negotiations with utilities, but we are still on target to open doors July 1, 2010. | In Progress | On target for July 1, 2010 occupancy
Objective #2: Promote conditions, behaviors and attitudes that result in a safer community
Department | Action | Measure | Target/Projection | Quarter 1 Update | Quarter 1 Comments | Quarter 2 Update | Quarter 2 Comments
911 CSD | A. Respond promptly and effectively to emergency assistance requests | 1. Percentage of calls answered in 5 seconds or less | 92.5% or greater | 94.7% |  | 94.9%
|  | 2. Percentage of calls answered in 10 seconds or less | 99.5% or greater | 99.8% |  | 99.9%
|  | 3. Average ring time | 3 seconds or less | 3 seconds |  | 3 seconds
|  | 4. Longest ring time | 10 seconds or less | 44 seconds | Currently being reviewed | 17 seconds
|  | 5. Call abandonment rate | No target set | 8.75% |  |  | Data being compiled to establish baseline
|  | 6. Average time to refer call to dispatch | 12 seconds or less | 12 seconds |  | 11 seconds
|  | 7. Implementation of quality improvement program for Emergency Response Center | Initial Implementation |  | Initial call review is being done. Program has been rolled out to the dispatch floor and will be touched on at upcoming inservice. | In Progress | Initial call review is being done. Program has been rolled out to the dispatch floor and will be touched on at upcoming inservice.
Community Justice | A. Put adult sex offenders and offenders assigned to electronic monitoring as a sanction placed on a device promptly | 1. Percentage of offenders placed on electronic device within 3 days | 90% or greater | 100% |  | 100%
| B. Get juvenile probationers with drug or alcohol use histories engaged in treatment | 1. Percentage of identified youth who have been evaluated, or have completed an educational or treatment program within 6 months | 75% or greater | 73.6% |  | 61%
| C. Reduce the number and frequency of juvenile offenders who re-offend | 1. Percentage of youth who do not re-offend during supervision | 87% or greater | 84.2% |  | 90%
| D. Provide opportunities for juveniles to repair harm to individuals and the community | 1. Percentage of juveniles who fulfill restitution obligation | 85% or greater | 67% |  | 78%
|  | 2. Percentage of juveniles who fulfill community service obligation | 85% or greater | 84% |  | 83%
| E. Get adult felony offenders on restitution caseload to pay restitution | 1. Percentage of adult offenders on restituiton caseload paying restitution | 45% or greater | 30% |  | 51%
District Attorney | A. Succesfully prosecute criminals | 1. Number of Driving Under the Influence of an Intoxicant (DUII) cases filed | 1400 | 350 in 1Q |  | 340 in 2Q; YTD = 690
|  | 2. Number of trials (Jury and Court, all cases) | 100 | 10 in 1Q |  | 12 in 2Q; YTD = 22
|  | 3. Number of major felony cases tried | 10 | 1 in 1Q |  | 4 in 2Q; YTD = 5
|  | 4. Number of major felony convictions | 10 | 1 in 1Q |  | 3 in 2Q; YTD = 4 | One hung jury, no decision
|  | 5.Number of Victim Notification | 2500 | 1,071 in 1Q |  | 944 in 2Q; YTD = 2,015
|  | 6. Percentage of attorneys completing continuing legal education and training | 100% |  |  | 100% | This figure refers to calendar year 2009
|  | 7. Number of juvenile delinquency petitions | 400 | 103 in 1Q |  | 63 in 2Q; YTD = 166
|  | 8. Number of juvenile dependency petitions | 50 | 11 in 1Q |  | 17 = 2Q; YTD = 28
| B. Promote programs to settle less serious cases, such as FASTtrack Accountability | 1. Number of FASTtrack Accountability cases | 500 | 111 in 1Q |  | 111 in 2Q; YTD = 222
|  | 2. Number of Family Drug Court cases | 25 | 25 in 1Q |  | 25 in 2Q | 25 is the maximum number of cases in the treatment court
|  | 3. Number of Mental Health Court cases | 25 | 18 in 1Q |  | 28 in 2Q | 7 pending applications; these figures represent the number in program at end of quarter; additions and graduations are ongoing
|  | 4. Number of Domestic Violence Treatment Court cases | 300 | 8 new cases in 1Q |  | 10 new cases in 2Q | Average approximately 300 cases in program at any given time; treatment typically lasts 18 months
Department | Action | Measure | Target/Projection | Quarter 1 Update | Quarter 1 Comments | Quarter 2 Update | Quarter 2 Comments
Sheriff's Office | A. Maintain current Adult Jail and Work Center programs available to inmates | 1. Number of inmates participating in programs | More than FY 2009 (???) | 151 |  | 127 in 2Q | Includes Restart and Motivational for Males and Females
| B. Ensure Adult Jail and Work Center are operated safely and efficiently | 1. Number of inmate incidents
| C. Respond to calls from community for public safety services | 1. Number of deputies per 1,000 residents | 1.02 | No update available | Population forecast not updated | YTD = 1.01 | Updated with the new PSU population Estimate for Deschutes County
|  | 2. Number of patrol calls for service | 24, 213 or less | 6574 |  | YTD = 11,188 | YTD slightly below same period prior year
|  | 3. Number of person and property crimes | 2339 | No update available | Next update available in Feb. 2010 | No update available | Next update available in Feb. 2010
|  | 4. Number of criminal cases per deputy | 50 | 43 | 300 cases and 7 detectives | 41 | 288 cases and 7 detectives
|  | 5. Number of civil papers processed | 12200 or more | 2631 |  | YTD = 5,360 | YTD slightly below same period prior year
|  | 6. Number of Search and Rescue missions | 138 or less | 32 |  | YTD = 72
Health Services | Maintain timely response to crisis needs in the community | 1. Percentage of mental health crises responded to within state standards | 100% | TBD- will report data semi-annual |  | YTD = 87.5%
|  | 2. Number of crises service hours provided | 3,200 or more | Q1 = 987 |  | YTD = 1641
|  | 3. Number of crises to which a response was received | 750 or more | Q1 = 261 | Based on number of clients seen in crisis since July 1, 2009 | YTD = 469 | Based on number of clients seen in crisis since July 1, 2009
Justice Court | A. Reduce outstanding receivable balance and increase collection rate | 1. Percentage increase in receivables | 10% or less | 1.4% |  | 2.2%
|  | 2. Rate of collection of fines | 74% or greater | 78% | Collections on fines imposed during this quarter | 80%
| B. Resolve small claims cases prior to trial | 1. Percentage of at-issue small claims cases resolved before trial | 85% or greater | 82% |  | 83%
| C. Decrease recidivism | 1. Recidivism rate | No measure provided |  | It is too labor intensive to measure this goal using our current software |  | It is too labor intensive to measure this goal using our current software
Objective #3: Maintain and strengthen current levels of diversion and alternative programs
Department | Action | Measure | Target/Projection | Quarter 1 Update | Quarter 1 Comments | Quarter 2 Update | Quarter 2 Comments
Community Justice | A. Have offenders in the domestic violence diversion program engaged in treatment | 1. Percentage of domestic violence offenders promptly engaged in treatment | 85% or greater | 74% |  | 76%
|  | 2. Percentage of domestic violence offenders completing treatment | 75% or greater | 59% |  | 63%
Health Services | A. Operate treatment courts through treatment, contracting and grant management | 1. Number of participants in Mental Health Court | 25 | 25 |  | 23
|  | 2. Percentage graduating from Mental Health Court | 75% or greater | 83% | Cumulative data since Jan. 1, 2002 | 84.6% | Cumulative data since Jan 1, 2002
|  | 3. Percentage of participants in Mental Health Court who re-offend | 13% or fewer | 13% | Cumulative data since Jan. 1, 2002 | 13% | Updated annually
|  | 4. Number of participants in Drug Court | 25 adults, 40 children | 25 adults, 40 children |  | 25 adults, 42 children
|  | 5. Percentage graduating or retained in Drug Court | 75% or greater | 42% | Cumulative data since inception 2006 | 54% | Cumulative data since 2006
|  | 6. Percentage of participants in Drug Court who -re-offend | 20% or fewer | 0% | Cumulative data since inception 2006 | 0% | Cumulative data since 2006
| B. Assist community reentry from County Jail for people with mental illness and addiction through the Bridge Program | 1. Number of participants in Bridge Program | 60 | 37 | Based on number served since July 1, 2009 | 44 | Since July 1, 2009
|  | 2. Percentage of enrolled clients retained in service | 50% or greater | 62% | Cumulative data since July 1, 2008 | 67% | Since July 1, 2008
|  | 3. Percentage of clients achieving a successful outcome | 60% or greater | 88% | Based on case management outcome this quarter only | 69% | This quarter only
|  | 4. Percentage of participants who re-offend | FY 2009 baseline | 21.6% | Updated annually. It is expected that this baseline will increase as data base expands | 21.6% | Same as first quarter
Objective #4: Lead and coordinate regional efforts in emergency preparedness
Department | Action | Measure | Target/Projection | Quarter 1 Update | Quarter 1 Comments | Quarter 2 Update | Quarter 2 Comments
Sheriff's Office | A. Meet or exceed all Oregon Emergency Management guidelines by leading disaster/pandemic exercises with all local resources | 1. Conduct disaster/pandemic exercises | Exercises completed by June 30, 2010 |  |  | Actual EOC activation | EOC activation in December (power outage). Actual activation usually counts for full scale exercise.
Health Services | A. Improve Deschutes County's ability and capability to respond to public health and other emergencies | 1. Percentage of Health Services preparedness leaders participating in the Health Alert Network emergency notification system | 90% or greater | 100% of ICS Team |  | 100% of ICS team
|  | 2. Percentage of staff with emergency response duties outlined in job description | 100% | 57% |  | 57%
| B. Develop and disseminate emergency preparedness information for vulnerable populations | 1. Number of caregivers of vulnerable County residents trained by June 30, 2010 | 200 caregivers | 35 (15%) |  | 68 People (68%) | Adult foster homes have been reached in entirety--a huge success.
|  | 2. Percentage of families in home visiting programs receiving preparedness information | 100% | 100% | Based on percentage of current active clients | 100% active clients | Based on number of current active clients
2. DIRECT SERVICES: Provide for direct services that enhance day-to-day quality of life and plan for future quality of life
Objective #1: Ensure accurate and timely assessment and taxation of property and recording of real property
Department | Action | Measure | Target/Projection | Quarter 1 Update | Quarter 1 Comments | Quarter 2 Update | Quarter 2 Comments
Assessor's Office | A. Timely appraisal of all new construction | 1. Percentage of new construction appraisals completed by August 1, 2009 | 100% | 100% |  | 100%
| B. Timely updating of name and map changes | 1. Percentage of assessment records with new Clerk recordings updated within three weeks | 100% | 100% |  | 100%
|  | 2. Average number of business days to update assessment record | 15 days or less |  |  | 15 days or less
|  | 3. Percentage of tax maps updated within three weeks | 100% | 100% |  | 100%
|  | 4. Average number of business days to update tax maps | 15 days or less |  |  | 15 days or less
| C. Timely certification of yearly assessment and tax roll | 1. Percentage of yearly assessment and tax rolls completed by Sept. 15, 2009 | 100% | 100% |  | 100% | Went smoothly
|  | 2. Percentage of tax statements mailed by October 25, 2009 | 100% | 100% |  | 100% | Only issue was the language in the tax insert regarding the Redmond School Bond
Clerk's Office | A. Timely recording of all real property records | 1. Percentage of real property records completed within 24 hours | 100% | 100% |  | 100%
| B. Timely process vital records and other documents accurately | 1. Percentage of marriage licenses accepted error free by Vital Records | 99% or greater | 99% |  | 100%
|  | 2. Percentage of declarations of domestic partnerships accepted error free by Vital Records | 99% or greater | 100% |  | 100%
|  | 3. Percentage of passports accepted error free by the State Department | 99% or greater | 100% |  | 100%
Objective #2: Address and plan for growth in Deschutes County
Department | Action | Measure | Target/Projection | Quarter 1 Update | Comments | Quarter 2 Update | Quarter 2 Comments
Community Development | A. Complete new Deschutes County Comprehensive Plan, including remapping process associated with destination resort overlay zone and update Transportation System Plan | 1. Comprehensive Plan approved by Board of Commissioners | By Oct. 31, 2010 | 25% complete | Draft Plan completed; presented to BOCC on 9/30/09 and Planning Commission 10/1/09. Public outreach on draft Plan has been initiated. | 40% complete | Draft Plan reviewed by Planning Commission and public; Responses being compiled
|  | 2. Transportation System Plan approved by Board of Commissioners | By Oct. 31, 2010 | 10% complete | In process of reviewing 2030 transportation and land use model predictions for traffic volumes; to identify future road improvements or policies; to update air, bike/ped, finance, rail elements of TSP. | 30% complete | Finalizing 2030 traffic volume predictions; completed rail element of TSP with Central Oregon Rail plan; worked with advocates to identify Three Sisters Scenic Bikeway; initiated Bend Airport Master Plan update for inclusion in TSP
|  | 3. Specific community plans for Tumalo, Terrebonne and Deschutes Junction completed, if appropriate | By Oct. 31, 2010 | 20% complete | Community Plans are in the process of being drafted. Community outreach will take place through October 2009 prior to draft completion and circulation. | 50% complete | Draft Plan distributed to three communities and Planning Commission; responses compiled; public hearing process could begin 4Q
| B. Provide timely and effective community development services | 1. Average turnaround time for land use application reviews | 60 days or less | 51 days |  | 55 days
|  | 2. Average turnaround time for building plan reviews | 5 days or less | 3 day |  | 3 day
|  | 3. Average score received on customer satisfaction questionnaire | 4.70 out of 5.00 or greater | 4.89 |  | 4.88 | 17 surveys received
Solid Waste | A. Maximize county resources for management of solid waste disposal | 1. Oregon Department of Environmental Quality (DEQ) acceptance of Cell 5 construction | By May 1, 2010 | 25% completed | Have executed contract for design and development of construction specifications | 75% completed | Design is completed and will be submitted to DEQ in 3Q; Expect approval in 3Q
|  | 2. Funding and timeline for improvements to Negus Transfer Station approved by Board of Commissioners | By June 30, 2010 | 0% completed | Continued decreases in waste flows and revenues may require putting this off until FY 2011. This will be re-evaluated later in the fiscal year. | 0% completed | Due to revenue shortfall, this action is unlikely in FY 2010
|  | 3. Number of violations or fines due to a failure to comply with federal or state guidelines | 0 | 0 | No violations or fines | 0 | No violations or fines
Objective #3: Develop long term plan for meeting road maintenance and construction needs
Department | Action | Measure | Target/Projection | Quarter 1 Update | Comments | Quarter 2 Update | Quarter 2 Comments
Road | A. Develop funding prioritization strategy | 1. Complete and implement funding prioritization strategy | By January 31, 2010 |  | Five-year projections for revenue and expenditures have been revised to reflect the implementation of the state transportation fundng bill. Road Maintenance funding report needs to be revisited. Revenue projections will also be used to develop the project prioritization scenario and CIP in the TSP update. |  | Funding strategies and road network priorities will be addressed in the county TSP update. TSP update in progress - possible adoption in Q4.
| B. Re-evaluate current road establishment moratorium based on outcome of 2009 state legislative session | 1. Rescind existing resolutions or approve new resolution regarding road establishment moratorium | By September 30, 2009 | 100% complete | BOCC signed resolution 2009-118 (Oct. 7, 2009) extending the road establishment moratorium | 100% Complete | BOCC signed resolution 2009-118 (Oct. 7, 2009) extending the road establishment moratorium
| C. Maintain high quality condition of county roads | 1. Percentage of roads rated good or better | 80% or greater | 64% | Percentage based on 2009 visual inspection data. Note: summer 2009 chip seal and preservation work has not yet been entered into data base - this will raise the % in the 2nd qtr. | 76% | Pavement condition has been updated to reflect chip seal and preservation work done in 2009.
| D. Update Pavement Management System data by conducting regular visual inspections of county roads | 1. Percentage of county arterials and collectors inspected | 100% | 100% | Department staff conducted visual inspection of the entire paved road system this past summer. | 100% Complete | Pavement inspections will be scheduled at regular intervals in future years (road segments will generally be inspected every-other year)
Objective #4: Conduct elections in an open, transparent, secure and accurate manner
Department | Action | Measure | Target/Projection | Quarter 1 Update | Comments | Quarter 2 Update | Quarter 2 Comments
Clerk's Office | A. Mail voter notification card and voter confirmation card within two weeks of registration | 1. Percentage of voter notification and voter confirmation cards mailed within two weeks | 95% or greater | 100% |  | 50% | Difficulty with card orders
3. NATURAL RESOURCES: Assess, protect and enhance the natural resources of Deschutes County
Objective #1: Support sound forest management practices
Department | Action | Measure | Target/Projection | Quarter 1 Update | Comments | Quarter 2 Update | Quarter 2 Comments
Natural Resource Protection | A. Collaborate and coordinate with U.S. Forest Service (USFS), Bureau of Land Managment (BLM), and state resource agencies on forest management issues | 1. Participate in environmental planning meetings, communicate with agency counterparts on new proposals project to ensure appropriate Best Management Practices (BMP) apply | 100% participation in project reviews | 100% participation | 3 meetings this quarter | 100% participation | 100% participation, 4 meetings in 2Q and various phone calls. Total meetings YTD = 7
| B. Provide substantive comment and involvement with land use decisions on public lands by providing input to Environmental Impact Studies (EIS) | 1. Percentage of EIS, EA and other environmental documents for which input provided | 95% of greater | 100% participation | 4 EA's and 1 EIS for comment this quarter | 100% participation | 100% participation, 6 environmental documents for review/comment in 2Q; Total YTD = 11
|  | 2. Number of field trips and other ground monitoring activities in which participated | 10 or greater | 4 Field Trips |  | 0 field trips in 2Q; Total YTD = 4
| C. Ensure BMP are followed on all county owned land, including fuels treatment | 1. Percentage of county land managed according to BMP | 100% | 100% | 6 contracts to administer. | 100% | 2 contracts to administer in 2Q; Total YTD = 8
|  | 2. Percentage of county land sold for which fuel treatment was accomplished prior to sale | 100% | 86% | Reviewed 21 properties, 18 in compliance, letters sent by Teresa Rosic | 86% | Reviewed 1 property, approved and followup with Property Management; Total reveiew YTD = 22, 19 in compliance
|  | 3. Approval of county policy or ordinance instituting BMP by Board of Commissioners | By June 30, 2010 | In Progress | Draft completed, will followup on policy letter | In Progress | Will have reviewed by Property Management and Solid Waste and have a letter for Dave Kanner's signature.
Objective #2: Enhance and protect groundwater and surface water in the Deschutes Basin
Department | Action | Measure | Target/Projection | Quarter 1 Update | Comments | Quarter 2 Update | Quarter 2 Comments
Community Development | A. Minimize the discharge of nitrates from onsite systems into the groundwater and surface water in Southern Deschutes County and other susceptible areas of the county | 1. In coordination with Department of Environmental Quality (DEQ), identify appropriate next steps in protecting south county groundwater, given the repeal of the Local Rule | By September 30, 2009 | 10% complete | DEQ has not yet discussed or announced any follow-up actions following the 7/22/09 joint public meeting. This is the first step in formulating the next steps of the County | 11% complete | DEQ announced meeting of stakeholder groups in 3Q leading to possible formation of stakeholder steering committee
|  | 2. Approval of Local Rule financial assistance plan by Board of Commissioners | By October 31, 2009 | 75% complete | Final adoption of the financial assistance plan will follow identification of next steps identified above. BOCC approved conceptual agreement with NeighborImpact in 9/09 to provide assistance to property owners in most dire need. | 75% complete | Final adoption of the financial assistance plan will follow identification of next steps identified above. Contract with NeighborImpact expected in 3Q
|  | 3. Implementation of high groundwater lot project and work plan | By April 30, 2010 | 10% complete | DEQ has not yet discussed or announced any follow-up actions following the 7/22/09 joint public meeting. This is the first step in formulating the next steps of the County | 10% complete | DEQ has not yet discussed or announced any follow-up actions following the 7/22/09 joint public meeting. This is the first step in formulating the next steps of the County
|  | 4. In conjunction with Sunriver, review and take appropriate action on the sewer feasibility study | By April 30, 2010 | 60% complete | Sunriver indicates the project is ahead of schedule and should be completed by 1/10. | 90% complete | Final report expected 3Q; work session with BOCC scheduled in 3Q
|  | 5. In coordination with DEQ, identify water quality impacts in other susceptible areas of Deschutes County | By June 30, 2010 | 0% complete | Coordination with DEQ has focused on South County water quality issue. | 0% complete | Coordination with DEQ has focused on South County water quality issue.
|  | 6. Rate of enforcing codes relating to failing onsite systems countywide | 100% | 100% | All identifed systems have been repaired. | 100% | All identifed systems have been repaired.
|  | 7. Identify measures to proactively address onsite system failures in areas susceptible to water quality impacts | By June 30, 2010 | 50% complete | Progress has been made toward providing financial assistance incentives for upgrades and repairs. | 90% complete | Rebate program for upgrades to nitrogen reducing systems adopted by BOCC in 3Q
|  | 8. Percentage of development approvals coordinated with required proactive measures | 100% | 95% | All new development has been required to install protective wastewater systems and approximately half of the residential additions have been required to upgrade their wastewater system. One property was granted a hardship exemption to Ord. 2008-019. | 100% | All new development has been required to install protective wastewater systems and approximately half of the residential additions have been required to upgrade their wastewater system. One property was granted a hardship exemption to Ord. 2008-019.
| B. Identify risk assocated with land use, stormwater, impacts to wetlands, floodplains and road maintenance that may negatively affect groundwater and surface water | 1. Implement new county practices and alter current county practices based on recommendations as part of Endangered Species Act risk assessment | By June 30, 2010 | 80% complete | Recommendations from Central Oregon ESA are incorporated into Comp Plan Update | 80% complete | Recommendations from Central Oregon ESA are incorporated into Comp Plan Update; Completion will occur upon BOCC adoption of Comp PLan and implementing ordinances
Objective #3: Support beneficial utilization of natural resources for economic development, tourism and recreation
Department | Action | Measure | Target/Projection | Quarter 1 Update | Comments | Quarter 2 Update | Quarter 2 Comments
Community Development | A. Define the full extent of natural wetlands in South Deschutes County | 1. Identify secure funding source for wetland project | By October 31, 2009 | 100% complete | Secured grant funding from Oregon Watershed Enhancement Board. RFQ will be published in November 2009 | 100% complete | Secured grant funding from Oregon Watershed Enhancement Board. RFQ will be published in November 2009
|  | 2. Complete delineation of wetlands | By June 30, 2010 | 0% complete | Local Wetland Inventory will take approximately 12 months. Expected completion is Fall 2010 / Winter 2011. | 10% complete | Personal service contract with ESA Adolfson being finalized; Work on Local Wetland Inventory should being in 3Q being completed in December 2010 or January 2011
|  | 3. Identify methods of protecting wetlands that provide environmental services in the form of wildlife habitat, water quality protection or improvement, flood mitigation and/or recreational benefits | By June 30, 2010 | 0% complete | Local Wetland Inventory will take approximately 12 months. Expected completion is Fall 2010 / Winter 2011. Investigation of possible protective measures will follow completion of LWI. | 0% complete | Local Wetland Inventory (LWI) will take approximately 12 months. Expected completion is December 2010/January 2011. Investigation of possible protective measures will follow completion of LWI and adopting it into the Comprehensive Plan. Adoption of LWI expected in Spring 2011.
| B. Update Goal 5 inventory of natural and commercial resources associated with the Comprehensive Plan | 1. Comprehensive Plan approved by Board of Commissioners | By October 31, 2010 | 10% complete | In the process of compiling all Goal 5 resources into a table. | 15% complete | In process
Fair and Expo Center | A. Provide positive economic impact on Deschutes County through utilization of the Fair and Expo facilities | 1. Economic Impact from fair and expo events and activities | $30 million or greater | 14506404 | July = $13,238,811; August = $309,918; September = $957,676; Total = $14,506,404 | Total YTD = $17,967,920 | October = $1,725,481; November = $1,437,741; December = $298,294; Total 2Q = $3,461,516;
|  | 2. Total number of visitors to the Deschutes County Fair | 245,000 visitors or more | 167,000 visitors | 196,635 to Fair & Expo Center; 167,000 to Fair; | 167,000 visitors to Fair
Road | A. Work cooperatively to promote and implement noxious weed control in Deschutes County | 1. Number of acres treated for noxious weeds | 3,500 acres or more | 561 acres in 1Q | A large portion of treatment work is done in the spring/early summer (4th qtr.). Appear to be on-track to meet target/projection. | 276 acres in 2Q; 837 acres YTD | A large portion of treatment work is done in the spring/early summer (4th qtr.). Appear to be on-track to meet target/projection.
Natural Resource Protection | A. Update, revise and implement community fire plans, treat fuels and provide education and prevention efforts to reduce area fires | 1. Number of Community Wildfire Protection Plan (CWPP) updates completed | 3 or more | 2 updated | Sunriver to be completed by years end. | 0 updated in 2Q | Sunriver meeting scheduled in 3Q
|  | 2. Percentage of grant requests approved for fuels treatment | 50% or greater | 80% approval | 4 grants received totalling $2.3, so far 80% success | 80% approval | YTD 4 grants received totalling $2.3
|  | 3. Number of CWPP Steering Committee meetings organized | 7 or more | 2 completed in 1Q |  | 2 completed in 2Q
|  | 4. Percentage of monthly Project Wildfire Steering Committee efforts and Fire Free activities attended | 100% | 100% |  | 100%
|  | 5. Number of acres treated on private and county owned land | 1,000 acres or more | 300 acres treated in 1Q |  | 400 acres treated in 2Q; 700 acres treated YTD
|  | 6. Percentage of treated acres using 100% utilization methods | 100% | 100% |  | 100%
Solid Waste | A. Promote recycling programs to reduce the proportion of solid waste production placed in the landfill | 1. Percentage of solid waste produced in Deschutes County that is recycled | 37% or greater | 37.4% | Data represents DEQ recovery rate | 37.4% | Goal achieved; Next calculation occurs in FY 2011
Property & Facilities | A. Cooperate with other government entities in developing and enhancing recreational opportunities through land trades | 1. Complete Bureau of Land Management (BLM) land trade | By June 30, 2012 | No Progress | This is such a low priority for BLM that it is essentially a dead project. | No progress | This is such a low priority for BLM that it is essentially a dead project.
|  | 2. Complete Division of State Lands (DSL) land trade | By June 30, 2010 | In Progress | DSL is conducting appraisals of selected properties as well as completing environmental assessments. County is updating our appraisals because they are now a year old. This process should be complete by early 2010, then we can proceed with the fomalities required for the trade. | Appraisals complete and in review | Hope to close transaction by mid-2010; Concern over each other's appraisal report; Need negotiation to agree on market values for South Redmond Tract and Fryrear Rd parcel; To equalize $1.3 million advantage to DSL, County options are: reduce size of acquired parcel, add cash or add land to exchange; DSL and BLM will apply jointly to partition 900+ acres to create South Redmond Tract; After County define acquisition, DSL begin to partitionit from 900+ acres; County and DSL share costs of surveying and land use action.
|  | 3. Acquire La Pine Rodeo property from BLM | By June 30, 2012 | In Progress | The ball is in BLM's court. They are supposed to be working on process, cost, roles, etc., then get back with the county for further discussion. |  | Revised draft of S1140 adds transfer of 10 acres to City of La Pine for library district; Size of proposed rodeo grounds educed to 150 acres; Sewer district expansion remains 750 acres; Field manager expressed concerns being addressed; Requested data from County Assessor to prepare opinion of value for parcels (professional appraisal later); Will meet with CDD to discuss zoning, wetlands, high groundwater and lack of sewer connection at site; County needs to be informed about suitability of parcel for rodeo grounds before incur costs and take title; Field manager unable to provide cost estimate for survey costs and other administrative costs that County required to pay; Continue try to identify how work to be accomplished and by which agency to estimate costs.
4. HEALTH SERVICES: Facilitate, invest in and provide a system of services to improve the health of Deschutes County residents
Objective #1: Partner and offer leadership on community initiatives
Department | Action | Measure | Target/Projection | Quarter 1 Update | Comments | Quarter 2 Update | Quarter 2 Comments
Commission on Children & Families | A. Increase awareness and improve service delivery for identified needs in the community to ensure children are healthy, protected and successful | 1. Develop and/or implement education and advocacy materials for the public | 2 to 4 projects | 4 Projects in 1Q | 1) Summer '09 How to Talk to Your Kids @ A&D - Bend-LaPine SD Booklet; 2) Fall '09 Coord School Health Project w/RSD; 3) Fall '09 Weed & Seed Juv. Crime Prev. Community Forums in Redmond; | 3 Projects in 2Q; 7 Projects YTD | 1) Summer '09 How to Talk to Your Kids @ A&D - Bend-LaPine SD Booklet; 2) Fall '09 Coord School Health Project w/RSD; 3) Fall '09 Weed & Seed Juv. Crime Prev. Community Forums in Redmond; 4) Fam Pres & Supp Initiative communication materials; 5) Ed Display & Materials for A&D Prev event @ Summit HS; 6) Party Safe Homes Materials for A&D Prev event @ Summit HS; 7) Darkness to Light child Abuse prev campaign;
| B. Increase the knowledge of status and needs of children, youth and families | 1. Number of contacts with policy makers, non-profit advocacy partners, service clubs, businesses & faith community | Establish baseline in FY 2010 | 3 Contacts in 1Q | 1) Human Services Forum w/Legislative Delegation; 2) Legislative Delegation w/CASTF; 3) Fight Crime Invest in Kids; | 7 Contacts in 2Q; 10 Contracts YTD | 1) Human Services Forum w/Legislative Delegation; 2) Legislative Delegation w/CASTF; 3) Fight Crime Invest in Kids;4) Community Schools Grant meetings w/ City of Sisters and Community Action Team of Sisters (CATS); 5) Commissioners Unger & Baney w/ State Coalition Strategic Planning Team; 6) Meeting w/ Sen. Merkley's assistant re; FAN appropriation; 7) Facilitate School-Based Health Center (SBHC) meeting, including reps from Cist of Sisters; 8) Juvenile Crime Prevention (JCP) Community Partners Planning Meeting, including Comm. Baney; 9) Annual Report meeting presentation to Governors Board and Legislative Delegation; 10) "Java with Judy" w/ Judy Stiegler re: Children & Youth Funding (CYF) and social service needs
|  | 2. Number of presentations or trainings to community groups, program professionals and/or policy makers | Establish baseline in FY 2010 | 3 Presentations in 1Q |  | 5 Presentations in 2Q; 8 Presentations YTD | 1) Kevin Campbell Family Find Training; 2) Motivational Interviewing Training; 3) A&D Prevention Progress Reports to DCHS AMH Committee; 4) Accounting for Domestic Violence in Child Custody Cases; 5) Staff & Board Reps on Deschutes County School District CS Teams in Madras; 6) Community Listening Circle; 7) High Desert Funding & Grantseeking Conf; 8) 5 Sisters CS Community Planning Meeting; 9) Weed & Seed Redmond;
|  | 3. Number of media contacts (newspaper, television, radio and website postings) | Establish baseline in FY 2010 | 2 Contacts in 1Q | 1) Kevin Campbell Training; 2) Domestic Violence in Child Custody Cases; | 6 Contact in 2Q; 8 Contacts YTD | 1) Kevin Campbell Family Find Training; 2) Motivational Interviewing Training; 3) A&D Prevention Progress Reports to DCHS AMH Committee; 3) LAUNCH Article; 4) Crime Prevention Funding for Younger kids; 5) SW Redmond Crime Prev Project; 6) La Pine Teen Center 7) Sisters CS Grant Initiative Project; 8) Central Oregon Family News
|  | 4. Number of households receiving biennial community report card on status of children, youth and families | Fall 2010 | No Data Available | Future: Include Distribution rate of newsletter and editorial/advocacy materials | No Data Available | Future: Include Distribution rate of newsletter and editorial/advocacy materials
| C. Bring community members together and offer leadership to address the needs and gaps identified by the Child Abuse Systems Task Force and Domestic Violence Council | 1. Number of identified gaps and needs in child abuse prevention and intervention continuum of services met | 2 or more | 3 Gaps and Needs Identified | 1) Exceeding Fam Pres & Supp Initiative goal for increasing # of foster care kids placed w/relatives; 2) Req. to DCCJ to provide supervision for misdemeanor strangulation in DV cases; 3) DV Council: Lethality Assessment training & GPS monitoring; | 3 Gaps and Needs Identified | 1) Exceeding Fam Pres & Supp Initiative goal for increasing # of foster care kids placed w/relatives; 2) Req. to DCCJ to provide supervision for misdemeanor strangulation in DV cases; 3) DV Council: Lethality Assessment training & GPS monitoring;
| D. Identify, develop, implement and advocate for policies to ensure children, youth and families are healthy, protected and successful | 1. Percentage of contracted programs in compliance with child abuse reporting agency | 100% | No Data Available | MOUs with Health Srevices Department and Juvenile Community Justice Department | No Data Available | MOUs with Health Srevices Department and Juvenile Community Justice Department
|  | 2. Percentage of contracted programs in compliance with criminal background check policy | 100% | 100% |  | 100%
| E. Invest in effective programs, projects and initiatives that improve the health, safety and success of children, youth and families | 1. Percentage of Ready*Set*Go parents who report reading to their children at least 3 times per week | 80% or greater | No Data Available |  | No Data Available | Data available by end of January
|  | 2. Percentage of children participating in Ready*Set*Go program with up-to-date immunizations compared with general population | 94% or greater | No Data Available |  | No Data Available | Data available by end of January
| F. Invest in prevention and intervention prorgams and initiatives to ensure children and youth are protected, healthy ahnd successful | 1. Number of employers adopting child care assistance programs in the work plpace | N/A | N/A | Program discontinued due to loss of funding | N/A | Program discontinued due to loss of funding
|  | 2. Percentage of child care providers that participate in professional development activities reporting an increase in knowledge and skills in early childhood care and education | 75% or greater | N/A | Program discontinued due to loss of funding | N/A | Program discontinued due to loss of funding
|  | 3. Percentage of registered child care providers who participate in professional development activities | 90% or greater | 100% |  | 100%
| G. Develop, help implement and manage the Deschutes County Juvenile Crime Prevention Plan and resources as required by state | 1. Juvenile Crime Prevention Plan developed and implemented | By July 1, 2010 | In Progress | Currently implementing 10-year plan which expires end of 2010. On track to meet targeted outcome date. | In Progress | On track to meet targeted outcome date.
|  | 2. Successfully implement 3 to 5 priorities in Juvenile Crime Prevention Plan | By July 1, 2010 | In Progress | Plan in development to be implemented Fall 2010. | In Progress | Plan in development to be completed April/May 2010, implemented Fall 2010.
| H. Invest in effective programs, projects and initiatives that prevent or reduce juvenile crime and improve the safety and success of at-risk youth | 1. Percentage of Juvenile Crime Prevention (JCP) funded programs, projects and initiatives meeting or exceeding all of their performance outcome measures | 95% or greater | No Data Available |  | 100% | All programs in this category are on target
|  | 2. Percentage of JCP programs meeting best practices criteria | 75% or greater | 100% |  | 100%
|  | 3. Percentage of youth participating in substance abuse prevention program reporting an increased awareness, development and use of one or more of the following taught skills: communication, cognitive processing, coping and decision making | 80% or greater | No Data Available |  | No Data Available | Data available by end of January
Department | Action | Measure | Target/Projection | Quarter 1 Update | Comments | Quarter 2 Update | Quarter 2 Comments
Health Services | A. Enhance the visibility of health services and access to care by reaching out to businesses, clinics and day care providers | 1. Percentage of medical clinics and day care providers contacted to improve disease reporting and immunization compliance | 50% or greater | 75% |  | 100% | Due to the H1N1 pandemic, we have been working very closely with clinics and have had personal contact and education with each one.
|  | 2. Number of children excluded from school for immunization noncompliance | 70 or less | No Data Available | Data available in February 2010 | Over 70 (exact number in next update) | Due to new vaccine requirements, there are going to be far more children excluded this year;
|  | 3. Number of new clients receiving family planning services through outreach to businesses not providing health insurance | 100 or more | 40 |  | 80
|  | 4. Number of referrals and percentage increase to Babies First through distribution of information to 8 clinics | 100% | Increase of 7 referrals | Distributed to 4 clinics | 100% | New screening program as CHC has greatly increased referrals to above goal.
|  | 5. Number of referrals and percentage increase to CaCoon from Neonatal Intensive Care Unit with help from neonatologists and nurse practitioners | 100% | 30 referrals, up from 0 | New screening program planned | 0 | New CHC program targets NICU families with Links 4 Health, not referring to BF-working on connection to it.
| B. Increase access to health services in North and South Deschutes County | 1. Number of La Pine residents provided reproductive services | 525 or more | 73 (14%) |  | 165 (31)%
|  | 2. Number of families receiving services at WIC clinic in Sisters | 145 or more | 0 | In process of securing space | space identified | IT working on connectivity options
|  | 3. Number of client visits at WIC clinic in La Pine | 405 or more quarterly | 369 |  | 360 | apts at capacity, looking for another clinic day in La Pine
|  | 4. Percentage of Oregon Health Plan members in each zip code receiving mental health services | 90% or greater of countywide average in each zip code |  | Data available in January 2010 | No data available | data will be available in Jan. 2010
| C. Support school-based health centers (SBHCs) by offering health and mental health care | 1. Number of school-based health centers state certified to operate | 3 or more | 3 certified | Planning grant for 2 more SBHCs | 3 certified | Planning grant for 2 more SBHCs
|  | 2. Number of child visits for health services | 2,000 or more | 257 visits (13%) | Data for period from Sept. 9 to Oct. 9 | 767 (38%)
|  | 3. Number of child visits for mental health services | Establish baseline in FY 2010 | No Data Available | Data available in January 2010 | No data available | Data will be available in Jan. 2010
Objective #2: Undertake preventive measures to reduce future demands for County and community services
Department | Action | Measure | Target/Projection | Quarter 1 Update | Comments | Quarter 2 Update | Quarter 2 Comments
Commission on Children & Families | A. Implement strategic plans with measurable prevention and intervention outcomes as adopted by the Board of Commissioners | 1. Successfully implement five priorities in the Commission on Children & Families Strategic Plan | Met or Exceed 5 Priorities | 3 Implemented | 1) Community Schools Initiative @RSD resulted in 41% improvement in reading scores;; 2) Reconn Families Initiative reducing # kids in foster care; 3) | 3 Implemented | 1) Community Schools Initiative @RSD resulted in 41% improvement in reading scores;; 2) Reconn Families Initiative reducing # kids in foster care; 3)
| B. Identify, create and take action on opportunities to increase monetary and non-monetary resources to address prioritized needs of children, youth and families | 1. Leveraged resources through cash match | Total for 2009 = $1.87M | 327033 | Funding fewer programs and leveraged resources for providers impacted by current economy; Other: 1) DV Custody Training $12,000; | 2Q Data not available | $327,033 in 1Q; Funding fewer programs and leveraged resources for providers impacted by current economy; Other: 1) DV Custody Training $12,000;
|  | 2. Leveaged resources through in-kind donations | Total for 2009 = $422,220 | 20825 |  | 2Q Data not available | $20,825 in 1Q
|  | 3. Leveraged resources through CCF and community partner volunteer hours | Total for 2009 = $16,922 | 3802 |  | 2Q Data not available | $3,802 in 1Q
|  | 4. Value of competitive state and federal grants received | Total for 2009 = $600,000; Total for 2008 = $374,940; Total for 2007 = $331,205 | 584716 | 1) Runaway & Homeless Youth $48,616; 2) SDFS $80,000 & $20,000 Gambling; 3) DFC $100,000; 4) Casey Mini-Grant $11,300; 5) FAN Fed Approp $238,000; 6) LAUNCH $37,500 CCF ($607,000 total); 7) Mary's Place $125,000; (This does not include $569,500/yr for LAUNCH Grant of which CCF receive a portion of total grant) | $586,270 YTD | 1) Runaway & Homeless Youth $48,616; 2) SDFS $80,000 & $20,000 Gambling; 3) DFC $100,000; 4) Casey Mini-Grant $11,300; 5) FAN Fed Approp $238,000; 6) LAUNCH $37,500 CCF ($607,000 total); 7) Mary's Place $125,000; (This does not include $569,500/yr for LAUNCH Grant of which CCF receive a portion of total grant; 8) Youth Suicide Prev $14,500; 9) CS Grant $5,000;
|  | 5. Develop streamlined and efficient system for tracking leveraged resources and volunteer hours | By June 30, 2010 | No Progress |  |  | Testing in Spring; Pilot to be ready by July 1, 2010
| C. Invest in prevention and intervention programs and initiatives proven to improve the health, safety and success of children, youth and families | 1. Percentage of local high risk families receiving intensive home visiting services demonstrating improved parent-child interactions | 70% or greater | No Data Available |  | No Data Available | Data available by end of January
|  | 2. Percentage of children assigned to CASA who did not experience re-abuse | 100% | 100% |  | 100%
|  | 3. Rate per 1,000 of substantiated reports of abuse or neglect for local Healthy Start families compared to rate among families in general population who are not served | 7 per 1,000 | No Data Available |  | No Data Available | Data available by end of January
|  | 4. Percentage of youth reconnected with family and/or in a stable and safe living situation before leaving homeless shelter | 100% | 98% |  | 2Q Data not available | Data available by end of January; 98% in 1Q
| D. Advocate for and invest in effective prevention and intervention programs, projects and initiatives promoting conditions, behaviors and attitudes resulting in a safer community | 1. Percentage of youth participating in mentoring program showing improved skills, attitudes and behaviors | 100% | 100% |  | 2Q Data not available | Data available by end of January; 100% in 1Q
|  | 2. Percentage of youth in homeless shelter demonstrating academic progress and re-engaged in school | 80% or greater | 82% |  | 2Q Data not available | Data available by end of January; 82% in 1Q
Department | Action | Measure | Target/Projection | Quarter 1 Update | Comments | Quarter 2 Update | Quarter 2 Comments
Health Services | A. With the community, adopt policies to reduce chronic disease in Deschutes County | 1. Number of health facilities, including the Health Services building, 100% tobacco free | 7 facilities total | 3 new facilities in 1Q; 7 facilities total | Added 3 sites with Health Services adoption | 0 new facilities in 2Q; Total YTD = 7 | No additional sites added since 1st quarter. Target of 7 met
|  | 2. Percentage of employees on the County insurance plan with a chronic disease directly contacted and offered disease management classes | 100% | 100% | Contact made via mail | 100% via letter
| B. Assure access to birth control services for Women in Need, reducing unplanned pregnancies | 1. Number of women at high rish of cervical cancer brought into care at Mosaic Medical with Deschutes County Health Services assistance | 12 women | 5 (41%) |  | 10 women YTD (83%)
|  | 2. Number of family planning client visits | 5,754 or more | 1,496 (26%) |  | 3,834 YTD (67)%
| C. Reduce spread of communicable diseases in the community | 1. Percentage above state average of 2 year olds immunized | 4% or greater | No Data Available | Data not available in 1Q | 0% Greater | Same as state: Deschutes 74% (State average 74%)
|  | 2. Percentage of cases in which others potentially exposed to sexually transmitted disease or HIV infections are contacted | 100% | 100% |  | 100%
| D. Increase screening and referral of clients with perinatal depression | 1. Percentage of maternity case management clients (with 3 or more home visits) screened for depression and referred | 75% or greater | 17% | Training completed on protocol | 67% | Training completed on protocol
| E. Expand the Early Assessment and Support Alliance | 1. Number of adolescents and young adults enrolled | 14 or more | 17 |  | 19
|  | 2. Percentage of Central Oregon estimated need (28) that is met | 50% or greater | 60% |  | 68%
| F. Provide intensive services to clients eligible for the Enhanced Care Program | 1. Percentage of clients able to remain in the community, avoiding more costly interventions | 95% or greater | 100% |  | 95%
| G. Respond to crisis situations in a timely manner, avoiding more costly | 1. Percentage of crisis referrals responded to within one business day | 100% | 100% |  | 100%
| interentions | 2. Percentage of crisis plans developed and implemented within one week | 100% | 100% |  | 100%
Objective #3: Provide health services in an effective and efficient manner
Department | Action | Measure | Target/Projection | Quarter 1 Update | Comments | Quarter 2 Update | Quarter 2 Comments
Commission on Children & Families | A. Invest in effective programs, projects and initiatives that improve the health, safety and success of children, youth and families | 1. Percentage of CCF sub-contracted programs, projects and initiatives meeting or exceeding all of their performance outcome measures | 95% or greater | 100% | 18/23 (78%) programs on target; 5/23 (22%) programs data not yet available | 100% | 18 of 23 (78%) programs on target; 5 programs data not yet available
| B. Efficiently manage, fund and oversee programs that get results | 1. Percentage of state and federal grant requirements being met (administrative rules and contract terms such as reporting criteria and deadlines) | 100% of state and federal grant funding requirements | 100% |  | 100%
|  | 2. Percentage of state and federal targeted outcomes and/or deliverables being met | 100% of targeted outcomes and/or deliverables for state and federal grants | 100% |  | 100%
|  | 3. Percentage of programs utlizing and/or meeting best practices criteria | 75% or greater | 100% |  | 100%
|  | 4. Percentageof sub-contracted programs completing quarterly reports on time | 100% | 100% |  | 100%
|  | 5. Percentage of sub-contracted programs with successfully completed site visits and/or self-assessment per biennium | 100% | No Data Available | Completed biennially. Target is to complete by end of FY 2010 | No Data Available | Completed biennially. Target is to complete by end of FY 2010
Health Services | A. Maintain a high level of direct client care and service | 1. Percentage of behavioral health FTE dedicated to direct services | 75% or greater | 80.1% |  | 80%
| B. Strengthen the new Health Services Department | 1. Report of actions with focus on service integration, effectiveness, efficiency and/or cost savings | By March 1, 2010 | No data available |  | No data available
| C. Assure contracted dollars result in beneficial services | 1. Percentage of health service contract measures met or exceeded | 80% or greater | No data available | data will be available in Jan. 2010 | No data available | Data will be available in Jan. 2010
| D. Maintain a high level of staff satisfaction as measured by the 2010 Employee Survey | 1. Job satisfaction index on Employee Survey | Exceed Countywide index | No data available | relying on 2010 survey | No data available | Relying on 2010 survey
| E. Maintain a high level of client care hours for health services | 1. Percentage of health clinicians achieving their service goals | (6 of 8) 75% or greater | 2 of 8 (25%) | home visiting nurses | 4 of 8 (50%) | Home visitig nurses & new hires
|  | 2. Percentage of state assigned caseload receiving WIC services | 105% or greater | 101% | recent caseload increase | 101%
|  | 3. Percentage of mental health clinicians achieving their service goals | 100% | No data available | data will be available in Jan. 2010 | No data available | Data will be available in Jan. 2010
| F. Sustain Oregon Health Plan funds for mental health | 1. Percentage of Oregon Health Plan funding documented as delivered services | 100% | No data available | data will be available in Jan. 2010 | No data available | Data will be available in Jan. 2010
| G. Help facilities and families care for seniors with mental health issues | 1. Percentage of clients requiring a higher, more costly level of service | 20% or less | No data available | working to develop method to measure | 10%
| H. Provide Family Support services to families with children with developmental disabilities so care can occur in the family home | 1. Percentage of families requesting out-of-home placement for their children | 5% or less | 3% |  | >1% (1 out of 148)
| I. Improve information management system | 1. Select an electronic record system for behavioral health | By January 31, 2010 | On schedule | RFP to be released Jan 2010 | On schedule | RFP to be released Jan 2010
|  | 2. Dedicate work group to cost OCHINs electronic record system for public health | By January 31, 2010 | 10%
| J. Improve accounts receivable and timely billing process | 1. Bring accounts receivable to no longer than 90 days for working claims | By August 31, 2009 | 0% | Projection Date change to 4/1/10. Due to State system billing issues, billing roles restructure, and implementation of measurable goals. |  | Projection Date change to April 1st due to State system billing issues, billing roles restructure, and implementation of measurable goals.
| K. Improve billing office procedures | 1. Create written procedures and work flows for billing office functions | By June 30, 2010 | 50%
5. SUPPORT SERVICES: Ensure that Deschutes County staff and decision makers have the knowledge, skills, resources and tools necessary to deliver quality public service
Objective #1: Assess, refine and expand, if necessary, the countywide training program
Department | Action | Measure | Target/Projection | Quarter 1 Update | Comments | Quarter 2 Update | Quarter 2 Comments
Administrative Services | A. Modify the training catalog to address the results of the Employee Survey and post training surveys | 1. Percentage of positive Employee Survey responses to training and education questions | 83% or greater | No Data Available | Fall/Winter training catalogue was distibuted in October. The catalogue includes classes requested by employees and superviors. |  | Fall/winter training classes taking place.
|  | 2. Track post training survey results | Establish baseline in FY 2010 | In Progress | Developing survey for class participants |  | Developing survey for class participants
Information Technology | A. Provide computer training classes supplemented with content pertinent to the County's computing environment | 1. Number of different training classes offered | 3 or more | In Progress | Discussions among IT staff have taken place and two staff members have been identified. The scope of this goal may change due to the avialabilty to training topics.
Objective #2: Evaluate and enhance customer service practices
Department | Action | Measure | Target/Projection | Quarter 1 Update | Comments | Quarter 2 Update | Quarter 2 Comments
Administrative Services | A. Establish coutywide standards for and measurement of customer service | 1. Training on countywide service standards provided in all departments | By September 30, 2009 | In Progress | Fall/Winter training catalogue includes 3 sessions on customer service training. |  | Completed 3 sessions on customer serivce training
|  | 2. Collect and track countywide customer service feedback | Establish baseline in FY 2010 | No Data Available | Will compare county customer service ratings after countywide resident survey. |  | Pending resident survey.
Information Technology | A. Create a mechanism for collecting customer service feedback pertaining to technology services offered | 1. Survey responses as a percentage of total requested | No measure provided | No Data Available | A general survey is planned for mid-FY 2010 after new services are rolled out
|  | 2. Measure of satisfaction with the quality of services provided | No measure provided | In Progress | Measure to be developed
|  | 3. Measure of the timeliness of services provided | No measure provided | In Progress | Measure to be developed
Sheriff's Office | A. Enhance off-duty training regimen to include more in-service training on more diverse topics | 1. Number of completed training hours for sworn and non-sworn staff | More than FY 2009 hours | 28 Hours | Higher than prior year | YTD = 68 hours | 40 hours of training offered by the Sheriff's Office Training Division in Qtr 2.
Objective #3: Ensure the county work environment is safe and conducive to productivity
Department | Action | Measure | Target/Projection | Quarter 1 Update | Comments | Quarter 2 Update | Quarter 2 Comments
Administrative Services | A. Provide training and education on policies and issues that effect workplace safety and productivity | 1. Establish workplace safety and productivity training and education program | By June 30, 2010 | In Progress | Safety training for employees is ongoing. Adopted new "Return to Work for Injured Employee" policy. Managing Employee Performance training was developed for all supervisors: 8 departments have been trained. |  | 10 depts have been training on Managing Employee Performance
Risk Management | A. Ensure facilities and equipment are maintained in a safe, comfortable and healthy condition | 1. County Days Away, Restricted or Transferred (DART) Rate & National Public Sector DART Rate | 1.35 or less | 2.04 | 4 DART incidents in 1Q; It is not unusual to start out very low or very high because each incident has a more significant effect on the DART rate. It is expected to drop as the year progresses. National rate not available in 1Q | 1.05 | 0 DART incidents in Q2. As predicted the rate is now dropping. There is a chance that some Q2 injuries will convert to DART reportables in Q3.
Property & Facilities | A. Ensure facilities and equipment are maintained in a safe, comfortable and healthy condition | 1. Percentage of failures for buildings and equipment with regular scheduled maintenance | Establish baseline in FY 2010 | No Data Available | Data to be provided at end of fiscal year | No data available | Data to be provided at end of fiscal year
|  | 2. Average response time to service requests | Establish baseline in FY 2010 | No Data Available | Data to be provided at end of fiscal year | No data available | Data to be provided at end of fiscal year
Objective #4: Effeciently and effectively use information technology to improve staff productivity and enhance customer service
Department | Action | Measure | Target/Projection | Quarter 1 Update | Comments | Quarter 2 Update | Quarter 2 Comments
Information Technology | A. Maintain appropriate level of cost for services | 1. Information Technology as percentage of total operating budget. | 1.54% | 1.54% | IT has negotiated an agreement with CDD to pay for 1/2 of their one web developer FTE for the remainder of the fiscal year. IT will uses these skills to complete an upgrade to the Couty Public website. IT will be using contingency to pay for this agreement which may have affect on the fiscal 2011 charges to departments. Though the IT operational budget went up this in FY 2010, all expenses in relation of operating the phone system were absorbed. IT has maintained approximately this same percentage for several years. There are no forseeable actions that would cause a radical change in this figure.
Sheriff's Office | A. Vendor and software for new Records Management System selected and project team operational | 1. Percentage of Records Management System replacement project completed by June 30, 2010 | 50% or greater | In Progress | Completed review of the first draft of the Needs Assessment Report | On Schedule | Continued RFP preparation. 911 E-Board approval of RFP expected in Qtr 3.
Objective #5: Provide ongoing evaluation of employee performance and employee job satisfaction
Department | Action | Measure | Target/Projection | Quarter 1 Update | Comments | Quarter 2 Update | Quarter 2 Comments
Administrative Services | A. Evaluate employee recognition program using quarterly employee feedback and 2010 Employee Survey | 1. Number of Employee Recognition Committee review sessions held | 4 | 1 held in 1st Quarter |  |  | No meeting held in 2Q; Will hold meeting to review input from employee survey on program; 1 meeting held in 1Q
|  | 2. Percentage of Employee Recognition Committee recommendations implemented within 90 days | 100% | 100% |  | 100%
Personnel | A. Track the number of employees voluntarily terminating their employment | 1. Employee voluntary (excluding lay-offs and discharges) turnover rate | 5.2% or less | 0.47% |  | 0.94%
| B. Track department head and supervisor ability to complete employee evaluations in a timely manner | 1. Percentage of employees leaving the county receiving an exit interview | 100% | 100% | This includes all employees with benefits (haf-time or more). Exit interviews are not given to employees without benefits, for example on-call or less than half0time employees | 100% | This includes all employees with benefits (haf-time or more). Exit interviews are not given to employees without benefits, for example on-call or less than half-time employees
|  | 2. Percentage of exit interview issues responded to accordingly | 100% | 100% |  | 100%
|  | 3. Percentage of employee evaluations completed within 30 days of employee anniversary date | 75% or greater | 65% | This covers employee evaluations for the months of June, July and August (due in July, August and September): June 55 of 76, July 93 of 128, August 32 of 75 | 69% for 2Q | This covers employee evaluations for the months of Sept., Oct, & Dec. (due in Oct., Nov & Dec.): Sept 83 of 114; Oct. 62 of 100; Nov. 60 of 83
Objective #6: Ensure fiscal responsibility in all aspects of county operations
Department | Action | Measure | Target/Projection | Quarter 1 Update | Comments | Quarter 2 Update | Quarter 2 Comments
Finance | A. Provide financial data to Budget Committee that is meaningful for decision making process, narrative information for all departments conforming to GFOA recommended budget requirements | 1. FY 2010 budget document complies with GFOA Distinctive Budget Award Criteria | Receive GFOA Certificate of Recognition for Budget Preparation Award for FY 2010 Budget Document | Pending | FY 09-10 Budget submitted to GFOA for the award -- we think it is in compliance and we will get the award | Achieved | We recently received notice that Deschutes County received the award for the second year
|  | 2. FY 2009 Comprehensive Annual Financial Report (CAFR) complies with GFOA Certificate of Achievement for Excellence in Financial Reporting criteria | Receive GFOA Certificate of Achievement Award for FY 2009CAFR Document | Pending | In progress -- expected to be completed by 12/15 | Pending | The CAFR was submitted on time and we expect to hear that we will again receive the "Certificate."
| B. Collect and distribute FY 2010 Tax Roll to all tax districts in a timely and cost-effective manner | 1. Tax statements issued by October 21, 2009 | 100% | In progress | Expected to be mailed on time | 100% | Tax statements were mailed on time and tax collections have gone well.
|  | 2. Tax distribution in a timely and cost-effective manner | Exceed ORS requirements | No data available |  | Achieved | Tax distributions to all taxing districts have been done in a timely manner
|  | 3. Number of tax accounts processed per FTE | 20,100 or more | No data available |  | No data available
Administrative Services | A. Identify and address departmental policies and procedures through development of audit work plan | 1. Audit Acceptance Rate for Deschutes County & National Average for Local Governments | 90% or greater | No Data Available | No audits completed in 1Q; National data not available in 1Q | 92% | 1 audit completed in 2Q; No change to national information
|  | 2. Percentage of follow-up workplans developed and sent to departments within 30 days of audit | 95% or greater | 100% |  | 100% | 1 workplan within 4 days
|  | 3. Percentage of follow-up audit reports completed within one year of audit | 100% | 50% | 2 completed - 305 days, 370 days | 100% in 2Q; 67% YTD | 1 follow-up within 275 days;
|  | 4. Post-audit customer satisfaction rate | 80% or greater | No Data Available | No responses during 1Q | 100% | 1 survey response received; 95% life to date response
| B. Procure funding for county and county-supported projects through successful preparation of grant application requests | 1. Percentage of grant requests made by the County that have been accepted | Establish baseline in FY 2010 | 100% (4 of 4) | 4 grant applications outstanding at beginning of FY 2010, 4 additional applications in 1Q total value of 8 applications = $2,060,311. In 1Q, 4 awarded for $913,291 and other 4 still pending. | 88% (7 of 8) | 4 grant applications outstanding at beginning of FY 2010, 3 funded for total award of $1,118,991; YTD 9 new applications submitted, 4 awarded for $935,813, 5 pending
Sheriff's Office | A. Provide quality support services at the lowest cost | 1. Direct cost per inmate | $107 or less | 106.81 |  | 111.22 | Average number of inmates less in Qtr 2
|  | 2. Number of non-sworn employees as a percentage of sworn employees | 26% or less | 27% |  | Dec 2009 = 28% | Higher percentage due to unfilled Jail and Patrol sworn approved positions.
| B. Maintain vehicle fleet to ensure officer and public safety | 1. Number of vehicles being maintained | 143 | 148 | Will fluctuate as new vehicles are purchased and old vehicles are sold | 164 | Budgeted new vehicles purchased in 2Q; Sale of excess vehicles will occur later in the year.
Road | A. Combine management of aggregate resources in the Road and Solid Waste Departments | 1. Savings from providing a county owned materials source for rock crushing | 130000 | 0 | Solid Waste plans to include rock crushing in upcoming bid for cell expansion project. Quantities and specifications for Road Department materials to be included in contract. |  | Solid Waste cell expansion project bids will open in 3Q. Contract includes rock crushing for Road Department (approximately 42,000 cubic yards of aggregate). Will calculate savings following bid award.
Solid Waste | A. Combine management of aggregate resources in the Road and Solid Waste Departments | 2. Savings from county owned land for excavation | 100000 | 0 | Expect to work with Road Department for rock processing during Cell 5 construction scheduled for 3Q. | 0 | Solicitation for construction bids releasaed, including rock processing which will supply aggregate for both departments needs

## Summarized
FY 2010 Deschutes County Goals and Objectives 2nd Quarter Summary Update
Goal 1: Public Safety
Objective #1: Long Term Needs | Action | Measure | 1Q | 2Q | 3Q | 4Q
Sheriff's Office | A. Corrections Facility | 1. Matrixing
| B. Mapping System | 1. Vehicle Accidents
| C. Digital Evidence System | 1. Install system
Health Services | A. Local Beds | 1. New beds
2. Total beds
3. Need met
Administrative Services | A. Funding for jail expansion | 1. Funding for jail construction
Property & Facilities | A. Construct OSP/911 building | 1. Complete construction
Objective #2: Safety Community | Action | Measure | 1Q | 2Q | 3Q | 4Q
911 CSD | A. Emergency assistance | 1. Calls answered <5 sec
2. Calls answered <10 sec
3. Avg ring time
4. Longest ring time
5. Call abandonment rate
6. Avg call referral time
7. Quality improvement program
Community Justice | A. Electronic monitoring | 1. On electronic device
| B. Drug and alcohol treatment | 1. Youth completed program
| C. Juvenile recidivism | 1. Youth re-offend
| D. Repair harm to community | 1. Fulfill restitution
2. Fulfill community service
| E. Adult restitution paid | 1. Offenders repay restitution
District Attorney's Office | A. Prosecute criminials | 1. DUII cases filed
2. Trials
3. Major felony cases tried
4. Major felony convictions
5. Victim notification
6. Continued education
7. Juvenile delinquency petitions
8. Juvenile dependency petitions
| B. Settle less serious cases | 1. FASTtrack cases
2. Family Drug Court cases
3. Mental Health Court cases
4. Dom. Violence Court cases
Sheriff's Office | A. Inmate programs | 1. Inmates in programs
| B. Jail operation | 1. Inmate incidents
| C. Community call responses | 1. Deputies per residents
2. Patrol calls for service
3. Person and property crimes
4. Criminal cases per deputy
5. Civil papers processed
6. Search & Rescue missions
Health Services | A. Mental health crises | 1. Timely crises response
2. Crises service hours
3. Crises response received
Justice Court | A. Reduce receivable balance | 1. Increase in receivables
2. Rate of collection of fines
| B. Resolve small claims cases | 1. Cases resolved before trial
| C. Decrease recidivism | 1. Recidivism rate
Objective #3: Diversion & Alternatives | Action | Measure | 1Q | 2Q | 3Q | 4Q
Community Justice | A. Domestic violent in treatment | 1. Engaged in treatment
2. Completing treatment
Health Services | A. Operate treatment courts | 1. In Mental Health Court
2. Mental Health Court graduates
3. Mental Health Court who re-offend
4. # in Drug Court
5. Drug Court graduates
6. Drug Court who re-offend
| B. Bridge Program | 1. In Bridge Program
2. Enrolled retaining service
3. Successful outcomes
4. Re-offenders
Objective #4: Emergency Preparedness | Action | Measure | 1Q | 2Q | 3Q | 4Q
Sheriff's Office | A. Meet state guidelines | 1. Disaster/pandemic exercises
Health Services | A. Response to emergencies | 1. Leaders in notification system
2. Duties in job description
| B. Distribution of information | 1. Caregivers trained
2. Info. to home visit families
|  | Goal #1 | 1Q | 2Q | 3Q | 4Q
|  | Met target | 0 | 2 | 2 | 2
|  | Meeting or on pace to meet target | 19 | 21
|  | Pending, in progress or no data available | 31 | 28
|  | Not meeting or on pace to not meet target | 15 | 14
|  | Did not meet target | 0 | 0 | 0 | 0
|  |  | 65 | 65 | 2 | 2
Goal 2: Direct Services
Objective #1: Assessment & Taxation | Action | Measure | 1Q | 2Q | 3Q | 4Q
County Assessor's Office | A. New construction appraisals | 1. Appraisals completed
| B. Name and map change | 1. Assement records updated
2. Days update assesment
3. Tax maps updated
4. Days update tax maps
| C. Certify assessment/tax roll | 1. Assessment/tax rolls completed
2. Tax statements mailed
County Clerk's Office | A. Real property records | 1. Property records completed
| B. Process vital records | 1. Marriage licenses error free
2. Domestic partnerships error free
3. Passports error free
Objective #2: Planning & Growth | Action | Measure | 1Q | 2Q | 3Q | 4Q
Community Development | A. Comprehensive Plan | 1. Comprehensive Plan approved
2. Trans. System Plan approved
3. Community plans completed
| B. Community development | 1. Land use review turnaround
2. Building plan review turnaround
3. Customer questionnaire
Solid Waste | A. Maximize resources | 1. Cell 5 construction accepted
2. Negus improvements approved
3. Guideline violations
Objective #3: Road Maintenance/Construction | Action | Measure | 1Q | 2Q | 3Q | 4Q
Road | A. Funding prioritization strategy | 1. Implement strategy
| B. Re-revaluate moratorium | 1. Rescind/approve resolution
| C. Maintain condition of roads | 1. Roads ratings
| D. Pavement Mgmt System data | 1. Arterials/collectors inspected
Objective #4: Elections | Action | Measure | 1Q | 2Q | 3Q | 4Q
County Clerk's Office | A. Voter notification cards | 1. Cards mailed
|  | Goal #2 | 1Q | 2Q | 3Q | 4Q
|  | Met target | 4 | 5 | 5 | 5
|  | Meeting or on pace to meet target | 14 | 12
|  | Pending, in progress or no data available | 6 | 5
|  | Not meeting or on pace to not meet target | 1 | 3
|  | Did not meet target | 0 | 0 | 0 | 0
|  |  | 25 | 25 | 5 | 5
Goal 3: Natural Resources
Objective #1: Forest Management | Action | Measure | 1Q | 2Q | 3Q | 4Q
Natural Resource Protection | A. Work with USFS & BLM | 1. Environmental planning meetings
| B. Env. Impact Studies | 1. EIS input
2. Field trips
| C. Best Mgmt Practices | 1. County land managed by BMP
2. Land sold with fuels treatment
3. Policy instituting BMP
Objective #2: Water Quality | Action | Measure | 1Q | 2Q | 3Q | 4Q
Community Development | A. Nitrates from onsite systems | 1. Next steps
2. Local Rule financial asst. plan
3. High groundwater lot project
4. Sunriver sewer feasibility study
5. Water quality impacts
6. Onsite sys. code enforcement
7. Address onsite system failures
8. Approvals with measures
| B. Water risk | 1. ESA risk assessment
Objective #3: Resource Utilization | Action | Measure | 1Q | 2Q | 3Q | 4Q
Community Development | A. Define natural wetlands | 1. Identify funding for project
2. Delineation of wetlands
3. Methods of protecting wetlands
| B. Inventory of resources | 1. Comprehensive Plan approved
Fair & Expo | A. Facilities economic impact | 1. Economic Impact of fair & expo
2. Visitors to County Fair
Road | A. Noxious weed control | 1. Acres treated
Natural Resource Protection | A. Community fire plans | 1. Comm. Wildfire Protection Plans
2. Fuels treatment grant requests
3. CWPP Committee meetings
4. Project Wildfire/Fire Free activities
5. Acres treated
6. Treated acres with utilization methods
Solid Waste | A. Recycle reduce landfill waste | 1. Recycled solid waste
Property & Facilities | A. Recreation from land trades | 1. Complete BLM land trade
2. Complete DSL land trade
3. La Pine Rodeo property from BLM
|  | Goal #3 | 1Q | 2Q | 3Q | 4Q
|  | Met target | 2 | 2 | 2 | 2
|  | Meeting or on pace to meet target | 8 | 9
|  | Pending, in progress or no data available | 18 | 17
|  | Not meeting or on pace to not meet target | 3 | 3
|  | Did not meet target | 1 | 1 | 1 | 1
|  |  | 32 | 32 | 3 | 3
Goal 4: Health Services
Objective #1: Community Initiatives | Action | Measure | 1Q | 2Q | 3Q | 4Q
Commission on Children & Families | A. Awareness/service delivery | 1. Communication projects
| B. Knowledge of needs | 1. Contacts
2. Presentations
3. Media cotacts
4. Households receiving report card
| C.child abuse prevention needs | 1.Gaps/needs where services met
| D. Advocate for policies | 1. Child abuse compliance reporting
2. Background check compliance
| E. Invest in programs | 1. Parents reading to children
2. Children immunized
| F. Prevention and intervention | 1. Employers with child care asst.
2. Child care report improvements
3. Child care in development activities
| G. Juvenile Crime Prev. Plan | 1. Develop and implement plan
2. Implement priorities in plan
| H. Juvenile crime prevention | 1. Meeting outcome measures
2. Meeting best practices criteria
3. Substance abuse improvement
Health Services | A. Reach out to businesses | 1. Disease reporting/imm. Compl.
2. No school for imm. non-compl.
3. Planning svc thru outreach
4. Referrals to Babies First
5. Referrals to CaCoon
| B. Access to health services | 1. La Pine given reproductive services
2. Sisters families with WIC svcs
3. Visits at WIC clinic in La Pine
4. OHP getting mental health svcs
| C. School-based health centers | 1. Centers state certified
2. Child visits for health services
3. Visits for mental health services
Objective #2: Preventive Measures | Action | Measure | 1Q | 2Q | 3Q | 4Q
Commission on Children & Families | A. Implement strategic plans | 1. Implement plan prioirities
| B. Resources for prioritized needs | 1. Cash match leverage
2. In-kind donation leverage
3. Volunteer hour leverage
4. Value of state and federal grants
5. Track resources and volunteer hours
| C. Prevention and intervention | 1. Families receiving home visits
2. CASA children not re-abused
3. Healthy Start families abuse/neglect
4. Stable situation before leaving shelter
| D. Safer community programs | 1. Mentor program improvement
2. Academic progress in shelter
Health Services | A. Reduce chronic disease | 1. Facilities tobacco free
2. Chronic disease empl. contacted
| B. Birth control service access | 1. Women brought to Mosaic Medical
2. Family planning client visits
| C. Communicable diseases | 1. 2 years olds immunized
2. STD or HIV exposed contacted
| D. Perinatal depression screenings | 1. Clients screened for depression
| E. Early Assess. & Supp. Alliance | 1. Enrolled
2. Need met
| F. Enhanced Care Program | 1. Able to remain in community
| G. Respond to crisis situation | 1. Crisis referrals response
2. Crisis plans developed timely
Objective #3: Effective & Efficient Care | Action | Measure | 1Q | 2Q | 3Q | 4Q
Commission on Children & Families | A. Invest in programs | 1. Meeting outcome measures
| B. Management of programs | 1. Grant obligations met
2. Contract target outcomes met
3. Programs meeting criteria
4. Quarterly reports completed
5. Site visits and self-assessment
Health Services | A. Direct client care and service | 1. Behavioral health to direct services
| B. Strengthen Department | 1. Report of actions
| C. Funding for beneficial services | 1. Contract measures met
| D. Staff satisfaction | 1. Job satisfaction index on survey
| E. Client hours for health services | 1. Health clinicians achieving goals
2. Assigned caseload receiving WIC
3. Mental health clinicians meet goals
| F. OHP funds for mental health | 1. OHP used for delivered services
| G. Facilities/family care for seniors | 1. Clients requiring higher level of service
| H. Developmentally disabled support | 1. Requets for out-of-home placement
| I. Information management system | 1. Electronic record system
2. Electronic record system group
| J. Account receivable/billing process | 1. Accounts receivable for claims
| K. Improve billing office procedures | 1. Create procedures and work flows
|  | Goal #4 | 1Q | 2Q | 3Q | 4Q
|  | Met target | 4 | 4 | 2 | 2
|  | Meeting or on pace to meet target | 24 | 23
|  | Pending, in progress or no data available | 38 | 37
|  | Not meeting or on pace to not meet target | 6 | 8
|  | Did not meet target | 2 | 2 | 2 | 2
|  |  | 74 | 74 | 4 | 4
Goal 5: Support Services
Objective #1: Training | Action | Measure | 1Q | 2Q | 3Q | 4Q
Administrative Services | A. Modify training catalog | 1. Positive survey responses
2. Track post training survey results
Information Technology | A. Computer training classes | 1. Training classes offered
Objective #2: Customer Service | Action | Measure | 1Q | 2Q | 3Q | 4Q
Administrative Services | A. Countywide standards | 1. Train all departments on standards
2. Track customer service feedback
Information Technology | A. Feedback for services | 1. Survey response
2. Satisfaction with service provided
3.Timeliness of service provided
Sheriff's Office | A. Off-duty training regimen | 1. Completed training hours for staff
Objective #3: Work Safety | Action | Measure | 1Q | 2Q | 3Q | 4Q
Administrative Services | A. Workplace safety training | 1. Training and education program
Risk Management | A. Facilities/equipment condition | 1. DART Rate
Property & Facilities | A. Facilities/equipment maintained | 1. Failures for buildings and equipment
2. Response time to service requests
Objective #4: Productivity from Technology | Action | Measure | 1Q | 2Q | 3Q | 4Q
Information Technology | A. Maintain cost for services | 1. IT as portion of operational budget
Sheriff's Office | A. Records Management System | 1. Project completion
Objective #5: Performance & Job Satisfaction | Action | Measure | 1Q | 2Q | 3Q | 4Q
Administrative Services | A. Employee recognition program | 1. Committee review sessions held
2. Recommendations implemented
Personnel | A. Employees voluntarily terminating | 1. Employee voluntary turnover rate
| B. Employee evaluations | 1. Receiving exit interview
2. Exit interviews responded to
3. Employee evaluations completed
Objective #6: Fiscal Responsibility | Action | Measure | 1Q | 2Q | 3Q | 4Q
Finance | A. Data to Budget Committee | 1. Budget complies with GFOA
2. CAFR complies with GFOA
| B. Tax roll to tax districts | 1. Tax statements issued timely
2. Tax distribution
3. Tax accounts processed per FTE
Administrative Services | A. Policies through audits | 1. County audit acceptance rate
2. Follow-up work plans developed
3. Follow-up audit reports completed
4. Post-audit customer satisfaction rate
Sheriff's Office | A. Support services at lowest cost | 1. Direct cost per inmate
2. Percentage non-sworn employees
| B. Maintain vehicle fleet | 1. Vehicles maintained
Road | A. Management of resources | 1. Savings from county rock crushing
Solid Waste | A. Management of resources | 1. Savings from county excavation
|  | Goal #5 | 1Q | 2Q | 3Q | 4Q
|  | Met target | 0 | 0 | 0 | 0
|  | Meeting or on pace to meet target | 9 | 13
|  | Pending, in progress or no data available | 21 | 13
|  | Not meeting or on pace to not meet target | 5 | 4
|  | Did not meet target | 0 | 0 | 0 | 0
|  |  | 35 | 30 | 0 | 0
|  | GRAND TOTAL | 1Q | 2Q | 3Q | 4Q
|  | Met target | 10 | 13 | 11 | 11
|  | Meeting or on pace to meet target | 74 | 78 | 0 | 0
|  | Pending, in progress or no data available | 114 | 100 | 0 | 0
|  | Not meeting or on pace to not meet target | 30 | 32 | 0 | 0
|  | Did not meet target | 3 | 3 | 3 | 3
|  |  | 231 | 226 | 14 | 14

## By Dept Summary
911 CSD
Goal | Objective | Action | Measure | 1Q | 2Q | 3Q | 4Q
1 | 2 | A. Emergency assistance | 1. Calls answered <5 sec
2. Calls answered <10 sec
3. Avg ring time
4. Longest ring time
5. Call abandonment rate
6. Avg call referral time
7. Quality improvement program
Administrative Services
Goal | Objective | Action | Measure | 1Q | 2Q | 3Q | 4Q
1 | 1 | A. Funding for jail expansion | 1. Funding for jail construction
5 | 1 | A. Modify training catalog | 1. Positive survey responses
2. Track post training survey results
| 2 | A. Countywide standards | 1. Train all departments on standards
2. Track customer service feedback
| 3 | A. Workplace safety training | 1. Training and education program
| 5 | A. Employee recognition program | 1. Committee review sessions held
2. Recommendations implemented
| 6 | A. Policies through audits | 1. County audit acceptance rate
2. Follow-up work plans developed
3. Follow-up audit reports completed
4. Post-audit customer satisfaction rate
Commission on Children and Families
Goal | Objective | Action | Measure | 1Q | 2Q | 3Q | 4Q
4 | 1 | A. Awareness/service delivery | 1. Communication projects
|  | B. Knowledge of needs | 1. Contacts
2. Presentations
3. Media cotacts
4. Households receiving report card
|  | C.child abuse prevention needs | 1.Gaps/needs where services met
|  | D. Advocate for policies | 1. Child abuse compliance reporting
2. Background check compliance
|  | E. Invest in programs | 1. Parents reading to children
2. Children immunized
|  | F. Prevention and intervention | 1. Employers with child care asst.
2. Child care report improvements
3. Child care in development activities
|  | G. Juvenile Crime Prev. Plan | 1. Develop and implement plan
2. Implement priorities in plan
|  | H. Juvenile crime prevention | 1. Meeting outcome measures
2. Meeting best practices criteria
3. Substance abuse improvement
4 | 2 | A. Implement strategic plans | 1. Implement plan prioirities
|  | B. Resources for prioritized needs | 1. Cash match leverage
2. In-kind donation leverage
3. Volunteer hour leverage
4. Value of state and federal grants
5. Track resources and volunteer hours
|  | C. Prevention and intervention | 1. Families receiving home visits
2. CASA children not re-abused
3. Healthy Start families abuse/neglect
4. Stable situation before leaving shelter
|  | D. Safer community programs | 1. Mentor program improvement
2. Academic progress in shelter
4 | 3 | A. Invest in programs | 1. Meeting outcome measures
|  | B. Management of programs | 1. Grant obligations met
2. Contract target outcomes met
3. Programs meeting criteria
4. Quarterly reports completed
5. Site visits and self-assessment
Community Development
Goal | Objective | Action | Measure | 1Q | 2Q | 3Q | 4Q
2 | 2 | A. Comprehensive Plan | 1. Comprehensive Plan approved
2. Trans. System Plan approved
3. Community plans completed
|  | B. Community development | 1. Land use review turnaround
2. Building plan review turnaround
3. Customer questionnaire
3 | 2 | A. Nitrates from onsite systems | 1. Next steps
2. Local Rule financial asst. plan
3. High groundwater lot project
4. Sunriver sewer feasibility study
5. Water quality impacts
6. Onsite sys. code enforcement
7. Address onsite system failures
8. Approvals with measures
|  | B. Water risk | 1. ESA risk assessment
3 | 3 | A. Define natural wetlands | 1. Identify funding for project
2. Delineation of wetlands
3. Methods of protecting wetlands
|  | B. Inventory of resources | 1. Comprehensive Plan approved
Community Justice
Goal | Objective | Action | Measure | 1Q | 2Q | 3Q | 4Q
1 | 2 | A. Electronic monitoring | 1. On electronic device
|  | B. Drug and alcohol treatment | 1. Youth completed program
|  | C. Juvenile recidivism | 1. Youth re-offend
|  | D. Repair harm to community | 1. Fulfill restitution
2. Fulfill community service
|  | E. Adult restitution paid | 1. Offenders repay restitution
| 3 | A. Domestic violent in treatment | 1. Engaged in treatment
2. Completing treatment
County Assessor
Goal | Objective | Action | Measure | 1Q | 2Q | 3Q | 4Q
2 | 1 | A. New construction appraisals | 1. Appraisals completed
|  | B. Name and map change | 1. Assement records updated
2. Days update assesment
3. Tax maps updated
4. Days update tax maps
|  | C. Certify assessment/tax roll | 1. Assessment/tax rolls completed
2. Tax statements mailed
County Clerk
Goal | Objective | Action | Measure | 1Q | 2Q | 3Q | 4Q
2 | 1 | A. Real property records | 1. Property records completed
1. Marriage licenses error free
2. Domestic partnerships error free
3. Passports error free
| 4 | A. Voter notification cards | 1. Cards mailed
District Attorney
Goal | Objective | Action | Measure | 1Q | 2Q | 3Q | 4Q
1 | 2 | A. Prosecute criminials | 1. DUII cases filed
2. Trials
3. Major felony cases tried
4. Major felony convictions
5. Victim notification
6. Continued education
7. Juvenile delinquency petitions
8. Juvenile dependency petitions
|  | B. Settle less serious cases | 1. FASTtrack cases
2. Family Drug Court cases
3. Mental Health Court cases
4. Dom. Violence Court cases
Health Services
Goal | Objective | Action | Measure | 1Q | 2Q | 3Q | 4Q
1 | 1 | A. Local Beds | 1. New beds
2. Total beds
3. Need met
| 2 | A. Mental health crises | 1. Timely crises response
2. Crises service hours
3. Crises response received
| 3 | A. Operate treatment courts | 1. In Mental Health Court
2. Mental Health Court graduates
3. Mental Health Court who re-offend
4. # in Drug Court
5. Drug Court graduates
6. Drug Court who re-offend
|  | B. Bridge Program | 1. In Bridge Program
2. Enrolled retaining service
3. Successful outcomes
4. Re-offenders
| 4 | A. Response to emergencies | 1. Leaders in notification system
2. Duties in job description
|  | B. Distribution of information | 1. Caregivers trained
2. Info. to home visit families
4 | 1 | A. Reach out to businesses | 1. Disease reporting/imm. Compl.
2. No school for imm. non-compl.
3. Planning svc thru outreach
4. Referrals to Babies First
5. Referrals to CaCoon
|  | B. Access to health services | 1. La Pine given reproductive services
2. Sisters families with WIC svcs
3. Visits at WIC clinic in La Pine
4. OHP getting mental health svcs
|  | C. School-based health centers | 1. Centers state certified
2. Child visits for health services
3. Visits for mental health services
| 2 | A. Reduce chronic disease | 1. Facilities tobacco free
2. Chronic disease empl. contacted
|  | B. Birth control service access | 1. Women brought to Mosaic Medical
2. Family planning client visits
|  | C. Communicable diseases | 1. 2 years olds immunized
2. STD or HIV exposed contacted
|  | D. Perinatal depression screenings | 1. Clients screened for depression
|  | E. Early Assess. & Supp. Alliance | 1. Enrolled
2. Need met
|  | F. Enhanced Care Program | 1. Able to remain in community
|  | G. Respond to crisis situation | 1. Crisis referrals response
2. Crisis plans developed timely
| 3 | A. Direct client care and service | 1. Behavioral health to direct services
|  | B. Strengthen Department | 1. Report of actions
|  | C. Funding for beneficial services | 1. Contract measures met
|  | D. Staff satisfaction | 1. Job satisfaction index on survey
|  | E. Client hours for health services | 1. Health clinicians achieving goals
2. Assigned caseload receiving WIC
3. Mental health clinicians meet goals
|  | F. OHP funds for mental health | 1. OHP used for delivered services
|  | G. Facilities/family care for seniors | 1. Clients requiring higher level of service
|  | H. Developmentally disabled support | 1. Requets for out-of-home placement
|  | I. Information management system | 1. Electronic record system
2. Electronic record system group
|  | J. Account receivable/billing process | 1. Accounts receivable for claims
|  | K. Improve billing office procedures | 1. Create procedures and work flows
Fair & Expo Center
Goal | Objective | Action | Measure | 1Q | 2Q | 3Q | 4Q
3 | 3 | A. Facilities economic impact | 1. Economic Impact of fair & expo
2. Visitors to County Fair
Finance
Goal | Objective | Action | Measure | 1Q | 2Q | 3Q | 4Q
5 | 6 | A. Data to Budget Committee | 1. Budget complies with GFOA
2. CAFR complies with GFOA
|  | B. Tax roll to tax districts | 1. Tax statements issued timely
2. Tax distribution
3. Tax accounts processed per FTE
Information Technology
Goal | Objective | Action | Measure | 1Q | 2Q | 3Q | 4Q
5 | 1 | A. Computer training classes | 1. Training classes offered
| 2 | A. Feedback for services | 1. Survey response
2. Satisfaction with service provided
3.Timeliness of service provided
| 4 | A. Maintain cost for services | 1. IT as portion of operational budget
Justice Court
Goal | Objective | Action | Measure | 1Q | 2Q | 3Q | 4Q
1 | 2 | A. Reduce receivable balance | 1. Increase in receivables
2. Rate of collection of fines
|  | B. Resolve small claims cases | 1. Cases resolved before trial
|  | C. Decrease recidivism | 1. Recidivism rate
Natural Resource Protection
Goal | Objective | Action | Measure | 1Q | 2Q | 3Q | 4Q
3 | 1 | A. Work with USFS & BLM | 1. Environmental planning meetings
|  | B. Env. Impact Studies | 1. EIS input
2. Field trips
|  | C. Best Mgmt Practices | 1. County land managed by BMP
2. Land sold with fuels treatment
3. Policy instituting BMP
| 3 | A. Community fire plans | 1. Comm. Wildfire Protection Plans
2. Fuels treatment grant requests
3. CWPP Committee meetings
4. Project Wildfire/Fire Free activities
5. Acres treated
6. Treated acres with utilization methods
Personnel
Goal | Objective | Action | Measure | 1Q | 2Q | 3Q | 4Q
5 | 5 | A. Employees voluntarily terminating | 1. Employee voluntary turnover rate
|  | B. Employee evaluations | 1. Receiving exit interview
2. Exit interviews responded to
3. Employee evaluations completed
Property & Facilities
Goal | Objective | Action | Measure | 1Q | 2Q | 3Q | 4Q
1 | 1 | A. Construct OSP/911 building | 1. Complete construction
3 | 3 | A. Recreation from land trades | 1. Complete BLM land trade
2. Complete DSL land trade
3. La Pine Rodeo property from BLM
5 | 3 | A. Facilities/equipment maintained | 1. Failures for buildings and equipment
2. Response time to service requests
Risk Management
Goal | Objective | Action | Measure | 1Q | 2Q | 3Q | 4Q
5 | 3 | A. Facilities/equipment condition | 1. DART Rate
Road
Goal | Objective | Action | Measure | 1Q | 2Q | 3Q | 4Q
2 | 3 | A. Funding prioritization strategy | 1. Implement strategy
|  | B. Re-revaluate moratorium | 1. Rescind/approve resolution
|  | C. Maintain condition of roads | 1. Roads ratings
|  | D. Pavement Mgmt System data | 1. Arterials/collectors inspected
3 | 3 | A. Noxious weed control | 1. Acres treated
5 | 6 | A. Management of resources | 1. Savings from county rock crushing
Sheriff's Office
Goal | Objective | Action | Measure | 1Q | 2Q | 3Q | 4Q
1 | 1 | A. Corrections Facility | 1. Matrixing
|  | B. Mapping System | 1. Vehicle Accidents
|  | C. Digital Evidence System | 1. Install system
| 2 | A. Inmate programs | 1. Inmates in programs
|  | B. Jail operation | 1. Inmate incidents
|  | C. Community call responses | 1. Deputies per residents
2. Patrol calls for service
3. Person and property crimes
4. Criminal cases per deputy
5. Civil papers processed
6. Search & Rescue missions
| 4 | A. Meet state guidelines | 1. Disaster/pandemic exercises
5 | 2 | A. Off-duty training regimen | 1. Completed training hours for staff
| 4 | A. Records Management System | 1. Project completion
| 6 | A. Support services at lowest cost | 1. Direct cost per inmate
2. Percentage non-sworn employees
|  | B. Maintain vehicle fleet | 1. Vehicles maintained
Solid Waste
Goal | Objective | Action | Measure | 1Q | 2Q | 3Q | 4Q
2 | 2 | A. Maximize resources | 1. Cell 5 construction accepted
2. Negus improvements approved
3. Guideline violations
3 | 3 | A. Recycle reduce landfill waste | 1. Recycled solid waste
5 | 6 | A. Management of resources | 1. Savings from county excavation