## City CIP Nov 11,2010
Fund Center | C/F Budget | Original Budget | Budget Changes | FY11 Budget (1) | Curr. Budget | Month Exp. | YTD Expenditure | Pur. Req. | Pur. Order | Expenditures & Encumbrances | Avail Budget | % Util | Explanation/Justification of Planned Uses of Current Funds | Timeline of use of Current Funds | Estimated Funding Usage by June 30, 2011 | Project Can be Closed Out? (Y/N)
* 1001001000 Mayor and City Council | 800000 | 0 | 0
P-00581 Council CIP Priority Initiatives | 800000 | 0 | 0 |  | 800000 | 0 | 0 | 0 | 0 | 0 | 800000 | 0%
* 1601001000 City Manager's Office | 571152 | 200000 | 0
CP-006 Project Contingencies | 571152 | 200000 | 0 | 200000 | 771152 | 0 | 0 | 0 | 0 | 0 | 771152 | 0%
* 1601003000 P3 Strategic Planning & Perf Measurement | 0 | 0 | 50000
P-00610 City's Performance Mgt Software Implementation | 0 | 0 | 50000 |  | 50000 | 3134.12 | 35406.62 | 0 | 0 | 35406.62 | 14593.38 | 70.81%
* 1603001000 City Link Project | 907795.74 | 0 | -50000
CT-001 Technology Projects-Nonposting | 77591.75 | 0 | -50000 |  | 27591.75 | 0 | 0 | 0 | 0 | 0 | 27591.75 | 0%
P-00235 800 MHZ Radio System | 830203.99 | 0 | 0 |  | 830203.99 | 0 | 129149.5 | 0 | 0 | 129149.5 | 701054.49 | 15.56%
* 1611001000 Communications Office | 17351.66 | 45000 | 0
P-00106 Communications Technology Account | 17351.66 | 45000 | 0 | 45000 | 62351.66 | 9362.5 | 26667.93 | 0 | 0 | 26667.93 | 35683.73 | 42.77%
* 1621001000 Office of Economic Development | 11961204.9 | 103000 | 152100
CP-002 Project Contingencies | 2693790.95 | 0 | 141000 |  | 2834790.95 | 0 | 0 | 0 | 0 | 0 | 2834790.95 | 0%
P-00167 Strategic Investment | 1325228.38 | 103000 | 1000 | 103000 | 1429228.38 | 0 | 0 | 0 | 0 | 0 | 1429228.38 | 0%
P-00169 Downtown Marketing | 35161.46 | 0 | 0 |  | 35161.46 | 0 | 0 | 0 | 5523.76 | 5523.76 | 29637.7 | 15.71%
P-00200 Jefferson School | 5415299.1 | 0 | -500 |  | 5414799.1 | 108231.85 | 493043.08 | 0 | 4921756.02 | 5414799.1 | 0 | 100%
P-00326 Relocation of Farmers Market | 167990 | 0 | 0 |  | 167990 | 0 | 0 | 0 | 0 | 0 | 167990 | 0%
P-00385 Workforce Development | 194721.65 | 0 | 0 |  | 194721.65 | 0 | 3547.35 | 0 | 0 | 3547.35 | 191174.3 | 1.822%
P-00395 Technology Incubator | 87834.56 | 0 | 0 |  | 87834.56 | 0 | 0 | 0 | 0 | 0 | 87834.56 | 0%
P-00422 Mkt St.Gar Community Mtg Room | 26373.42 | 0 | 0 |  | 26373.42 | 0 | 0 | 0 | 0 | 0 | 26373.42 | 0%
P-00515 Shop Local Campaign | 932.99 | 0 | 0 |  | 932.99 | 0 | 0 | 0 | 0 | 0 | 932.99 | 0%
P-00530 Hillsdale Drive Phase I | 998361.84 | 0 | 0 |  | 998361.84 | 0 | 706665.82 | 0 | 248655.2 | 955321.02 | 43040.82 | 95.69%
P-00574 Affordable Housing Dev Incentive Program | 1000000 | 0 | 0 |  | 1000000 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0%
P-00575 Apprentice Program | 15510.55 | 0 | 0 |  | 15510.55 | 0 | 12174.75 | 0 | 0 | 12174.75 | 3335.8 | 78.49%
P-00609 Cherry Avenue Street Design Project | 0 | 0 | 10600 |  | 10600 | 0 | 9650 | 0 | 950 | 10600 | 0 | 100%
* 2101001000 Information Technology Operations | 76982.77 | 0 | 0
P-00231 IT Hardware | 76982.77 | 0 | 0 |  | 76982.77 | 0 | 44763.25 | 0 | 18227.5 | 62990.75 | 13992.02 | 81.82%
* 2301001000 Office of the Registrar | 1185.37 | 0 | 0
P-00566 Electronic Poll Books | 1185.37 | 0 | 0 |  | 1185.37 | 0 | 0 | 0 | 0 | 0 | 1185.37 | 0%
* 2401001000 Public Works Administration | 7789476.46 | 625669 | 139069
CP-004 Facilities Improvements | 386006.2 | 0 | 0 |  | 386006.2 | 0 | 14225 | 0 | 2798 | 17023 | 368983.2 | 4.41%
P-00103 CATEC - Improvements | 125549.13 | 31669 | 0 | 31669 | 157218.13 | 11225 | 21220 | 0 | 400 | 21620 | 135598.13 | 13.75%
P-00115 Facilitites Maintenance Renovation | 58710.11 | 0 | 0 |  | 58710.11 | 0 | 7421.07 | 0 | 13278.04 | 20699.11 | 38011 | 35.26%
P-00192 Wayland House Roof/Basement | 16717.23 | 0 | 0 |  | 16717.23 | 0 | 1165 | 0 | 0 | 1165 | 15552.23 | 6.969%
P-00197 Courts Study | 727782.17 | 0 | 0 |  | 727782.17 | 0 | 24762.75 | 0 | 0 | 24762.75 | 703019.42 | 3.402%
P-00349 Fire Station HQ Expansion | 2128173.65 | 0 | 0 |  | 2128173.65 | 0 | 0 | 0 | 0 | 0 | 2128173.65 | 0%
P-00426 CATEC - Major Facility Improvements | 152633.1 | 0 | 139069 |  | 291702.1 | 754 | 108723.55 | 0 | 43289.23 | 152012.78 | 139689.32 | 52.11%
P-00433 Ivy Rd/Fontaine Area Station Replacement | 4186068.18 | 0 | 0 |  | 4186068.18 | 21662.97 | 60603.15 | 0 | 838367.46 | 898970.61 | 3287097.57 | 21.48%
P-00495 CHS Girls Softball Field Lighting | 7836.69 | 0 | 0 |  | 7836.69 | 0 | 0 | 0 | 0 | 0 | 7836.69 | 0%
P-00595 Market Street Parking Garage Concrete Repairs | 0 | 594000 | 0 | 594000 | 594000 | 0 | 11900 | 0 | 47600 | 59500 | 534500 | 10.02%
SH-002 School Projects Unallocated - FY 2008 | 278331.4 | 0 | 0 |  | 278331.4 | 0 | 278251.51 | 0 | 79.89 | 278331.4 | 0 | 100%
SH-003 School Small Cap Projects | 295602.13 | 200000 | 115000 | 200000 | 610602.13 | 4262 | 164142.73 | 6.25 | 11089.7 | 175238.68 | 435363.45 | 28.7%
CP-005 Facilities Improvements - FY 2008 | 279573.68 | 0 | 0 |  | 279573.68 | 3161.43 | 9792.16 | 0 | 33241.28 | 43033.44 | 236540.24 | 15.39%
SH-009 School-09 | 487012.29 | 0 | 0 |  | 487012.29 | 0 | 484253.29 | 0 | 2759 | 487012.29 | 0 | 100%
CP-009 Facility Improvements 09 | 1095001.16 | 0 | 0 |  | 1095001.16 | 835 | 318536.18 | 0 | 198507.59 | 517043.77 | 577957.39 | 47.22%
SH-010 FY10 School Lump Sum | 1637313.4 | 0 | 0 |  | 1637313.4 | 513.6 | 123089.81 | 0 | 5438.62 | 128528.43 | 1508784.97 | 7.85%
CP-010 FY10 Facilities LS | 690734.2 | 0 | 0 |  | 690734.2 | 63064 | 209413.3 | 0 | 13281 | 222694.3 | 468039.9 | 32.24%
SH-011 FY11 Schools Lump Sum SH-011 | 0 | 1068463 | 541937.89 | 1068463 | 1610400.89 | 0 | 126580.48 | 0 | 86392.52 | 212973 | 1397427.89 | 13.22%
CP-011 FY11 Facilities Lump Sum CP-011 | 0 | 1068463 | 0 | 1068463 | 1068463 | 0 | 33322.05 | 0 | 36005 | 69327.05 | 999135.95 | 6.488%
* 2422001000 Public Works/School Maintenance | 39981.32 | 0 | 0
SH-050 School Small Cap Projects | 39981.32 | 0 | 0 |  | 39981.32 | 0 | 1949.55 | 0 | 37974.85 | 39924.4 | 56.92 | 99.86%
* 2422003000 School Maintenance/HVAC | 437325.27 | 500000 | 0
SH-060 School HVAC Replacement | 437325.27 | 500000 | 0 | 500000 | 937325.27 | 884 | 171033.31 | 0 | 2248.5 | 173281.81 | 764043.46 | 18.49%
* 2431001000 Public Service Administration | 377103.64 | 0 | 0
P-00350 Sidewalk Repair | 377103.64 | 0 | 0 | 296851 | 377103.64 | 2824.32 | 39325.15 | 0 | 13390.37 | 52715.52 | 324388.12 | 13.98%
* 2443001000 Streets and Sidewalks | 1096111.92 | 1901409 | -100000
P-00219 Signal Coordination /ITS | 0 | 100000 | -100000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
P-00350 Sidewalk Repair | 0 | 296851 | 0 |  | 296851 | 0 | 0 | 0 | 0 | 0 | 296851 | 0%
SS-007 Streets and Sidewalks (427) | 1096111.92 | 1504558 | 0 | 1504558 | 2600669.92 | 0 | 690112.09 | 0 | 1898507.09 | 2588619.18 | 12050.74 | 99.54%
* 2453001000 Stormwater | 34721.17 | 0 | 0
P-00470 Emergency DPW Citywide Drainage | 34721.17 | 0 | 0 |  | 34721.17 | 0 | 588.65 | 0 | 0 | 588.65 | 34132.52 | 1.695%
* 2471001000 Traffic Engineering | 128107.95 | 0 | 100000
P-00219 Signal Coordination /ITS | 128107.95 | 0 | 100000 | 100000 | 228107.95 | 1640.85 | 22360.88 | 0 | 17157.93 | 39518.81 | 188589.14 | 17.32%
* 2713001000 Gas Stormwater | 766189.11 | 350000 | 0
DR-002 Water Resources Protection Program | 766189.11 | 0 | 350000 | 350000 | 1116189.11 | 98954.47 | 503282.96 | 0 | 172980.52 | 676263.48 | 439925.63 | 60.59%
P-00535 Citywide Stormwater Initiatives | 0 | 350000 | -350000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
* 2801001000 Transit System | 454947.06 | 0 | 0
P-00211 Replace Transit Facility Avon | 454947.06 | 0 | 0 |  | 454947.06 | 0 | 322953.69 | 0 | 76550 | 399503.69 | 55443.37 | 87.81%
* 2804001000 Transit - Capital | 354403.71 | 316730 | 0
P-00334 CTS Bus and Bus Related Purchases | 354403.71 | 316730 | 0 | 316730 | 671133.71 | 0 | 32793.76 | 0 | 0 | 32793.76 | 638339.95 | 4.886%
* 2901001000 Fleet Maintenance Operations | 2.8 | 0 | 0
P-00583 Fleet Fuel Force System Upgrade | 2.8 | 0 | 0 |  | 2.8 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0%
* 3101001000 Police Administration | 475960.89 | 0 | 0
P-00236 Mobile Data Computers (MDC) Police | 475960.89 | 0 | 0 |  | 475960.89 | 0 | 0 | 0 | 6625.23 | 6625.23 | 469335.66 | 1.392%
* 3201001000 Fire Department Administration | 126243.84 | 0 | 0
P-00119 Fire Stations/Equipment/Beds | 1441.63 | 0 | 0 |  | 1441.63 | 0 | 0 | 890 | 0 | 890 | 551.63 | 61.74%
P-00435 Mobile Data Terminals Fire | 124802.21 | 0 | 0 |  | 124802.21 | 0 | 3473.76 | 0 | 0 | 3473.76 | 121328.45 | 2.783%
* 3211001000 Fire Fighting | 1999244 | 0 | 0
P-00591 Fire Trucks (2 Trucks - 2010) | 1999244 | 0 | 0 |  | 1999244 | 0 | 1595331 | 0 | 0 | 1595331 | 403913 | 79.8%
* 3611001000 Recreation Administration | 1798424.41 | 0 | 208250
P-00180 Percent for Art | 118157.32 | 0 | 0 |  | 118157.32 | 0 | 9934.72 | 0 | 0 | 9934.72 | 108222.6 | 8.408%
P-00207 McIntire Park - Phase II | 83647.8 | 0 | 0 |  | 83647.8 | 0 | 0 | 0 | 0 | 0 | 83647.8 | 0%
P-00208 Greenbelt / Bike Trails | 121604.35 | 0 | 33250 | 77250 | 154854.35 | 263.28 | 34514.86 | 0 | 44437.32 | 78952.18 | 75902.17 | 50.98%
P-00521 Brand Art Project | 20670.44 | 0 | 0 |  | 20670.44 | 0 | 0 | 0 | 0 | 0 | 20670.44 | 0%
P-00538 Coal Tower/Meade Ave Trail | 113000 | 0 | 0 |  | 113000 | 168.5 | 290 | 0 | 0 | 290 | 112710 | 0.2566%
P-00546 250 Bypass Commuter Trail | 289057.05 | 0 | 0 |  | 289057.05 | 0 | 0 | 0 | 10626.3 | 10626.3 | 278430.75 | 3.676%
P-00547 Trails-Safe Routes to Schools | 345310.79 | 0 | 0 |  | 345310.79 | 0 | 0 | 0 | 0 | 0 | 345310.79 | 0%
P-00548 Moore's Creek Trail | 19871.16 | 0 | 30000 |  | 49871.16 | 0 | 9826.33 | 0 | 0 | 9826.33 | 40044.83 | 19.7%
P-00549 Meadowcreek Trail | 37722 | 0 | 20000 |  | 57722 | 0 | 1950 | 0 | 0 | 1950 | 55772 | 3.378%
P-00550 Rivanna River Trail | 50000 | 0 | 25000 |  | 75000 | 0 | 5597 | 0 | 203 | 5800 | 69200 | 7.733%
P-00551 Trails-Parks Internal | 50000 | 0 | 0 |  | 50000 | 29.7 | 75.72 | 0 | 0 | 75.72 | 49924.28 | 0.1514%
P-00578 Schenk's Greenway | 50000 | 0 | 0 |  | 50000 | 0 | 0 | 0 | 0 | 0 | 50000 | 0%
P-00588 Wahsington Park Pool/Bathhouse Repairs | 499383.5 | 0 | 100000 | 100000 | 599383.5 | 219722.84 | 219967.09 | 0 | 322076.74 | 542043.83 | 57339.67 | 90.43%
* 3612001000 Recreation Maintenance | 199513.51 | 0 | 0
P-00143 Recreation Fac.Improvements & Main. | 8305.31 | 0 | 0 |  | 8305.31 | 0 | 0 | 0 | 0 | 0 | 8305.31 | 0%
P-00145 Forest Hills Recreation Bldg | 5337.21 | 0 | 0 |  | 5337.21 | 0 | 1264.75 | 0 | 2609.81 | 3874.56 | 1462.65 | 72.6%
P-00158 Onesty Pool | 185870.99 | 0 | 0 |  | 185870.99 | 0 | 0 | 0 | 0 | 0 | 185870.99 | 0%
* 3671001000 Parks and Mainteance | 3576151.85 | 1205250 | -178250
P-00144 Downtown Mall Repair | 31122.63 | 0 | 0 |  | 31122.63 | 0 | 0 | 0 | 0 | 0 | 31122.63 | 0%
P-00148 Parks Master Plan | 3569.4 | 0 | 0 |  | 3569.4 | 0 | 0 | 0 | 0 | 0 | 3569.4 | 0%
P-00150 Landscape Beautification | 40382.13 | 0 | 0 |  | 40382.13 | 0 | 14432 | 0 | 0 | 14432 | 25950.13 | 35.74%
P-00208 Greenbelt / Bike Trails | 31000 | 77250 | -108250 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
P-00330 Parks Playground Improvements | 81733.16 | 103000 | 0 | 103000 | 184733.16 | 2995.95 | 37596.29 | 0 | 74061.54 | 111657.83 | 73075.33 | 60.44%
P-00428 Urban Tree Preservation and Planting | 277241.08 | 50000 | 0 | 50000 | 327241.08 | 11341.8 | 13766.46 | 0 | 0 | 13766.46 | 313474.62 | 4.207%
P-00430 Neighborhood Center Repairs and Renovations | 1622.23 | 0 | 0 |  | 1622.23 | 0 | 0 | 0 | 0 | 0 | 1622.23 | 0%
P-00492 Smith Pool | 2711681.22 | 0 | 0 |  | 2711681.22 | 57740.84 | 2091765.17 | 239.94 | 262596.62 | 2354601.73 | 357079.49 | 86.83%
P-00534 Parkland Acquisition | 97800 | 250000 | 0 | 250000 | 347800 | 0 | 2861 | 0 | 200 | 3061 | 344739 | 0.8801%
P-00538 Coal Tower/Meade Ave Trail | 300000 | 0 | 0 |  | 300000 | 0 | 0 | 0 | 0 | 0 | 300000 | 0%
P-00588 Wahsington Park Pool/Bathhouse Repairs | 0 | 100000 | -100000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
P-00594 YMCA Pool (City Share) | 0 | 625000 | 0 | 625000 | 625000 | 0 | 0 | 0 | 0 | 0 | 625000 | 0%
P-00599 Azalea Park | 0 | 0 | 30000 |  | 30000 | 0 | 0 | 0 | 0 | 0 | 30000 | 0%
* 3901001000 Neighborhhood Dev Serv - Administration | 18286995.69 | 26270166 | 941400
2000020 Historic Preservation Loans | 2481.35 | 0 | 0 |  | 2481.35 | 0 | 0 | 0 | 0 | 0 | 2481.35 | 0%
CP-001 Neighborhood Development Services CIP | 105726.9 | 100000 | -5600 | 100000 | 200126.9 | 0 | 36843.5 | 92.77 | 66266.02 | 103202.29 | 96924.61 | 51.57%
P-00127 Undergrounding Utilities | 182000 | 100000 | 0 | 100000 | 282000 | 0 | 282000 | 0 | 0 | 282000 | 0 | 100%
P-00130 Wayfinding | 491181.95 | 0 | 0 |  | 491181.95 | 442706 | 442706 | 0 | 40580.15 | 483286.15 | 7895.8 | 98.39%
P-00156 Major Downtown Mall Renovation | 322550.68 | 0 | 0 |  | 322550.68 | 9357.17 | 239399.62 | 0 | 18626.68 | 258026.3 | 64524.38 | 80%
P-00178 5th & Water St. Site Improvement | 165691.35 | 0 | 0 |  | 165691.35 | 0 | 127499.48 | 0 | 31680 | 159179.48 | 6511.87 | 96.07%
P-00201 Rte 250 Byp Interchange at McInitre | 7203743.08 | 23686166 | 0 | 23686166 | 30889909.08 | 0 | 4871.16 | 0 | 2945512.12 | 2950383.28 | 27939525.8 | 9.551%
P-00204 2nd Street Improvements | 89191.23 | 0 | 447000 |  | 536191.23 | 177729.75 | 387221.35 | 0 | 114597.79 | 501819.14 | 34372.09 | 93.59%
P-00212 JPA Bridge VDOT 14645 (2%) | 104941.17 | 100000 | 0 | 100000 | 204941.17 | 0 | 625.87 | 0 | 0 | 625.87 | 204315.3 | 0.3054%
P-00214 Bridge Inspections & Repairs | 686243.12 | 159000 | 0 | 159000 | 845243.12 | 600 | 600 | 0 | 50000 | 50600 | 794643.12 | 5.986%
P-00216 Hillsdale Drive Connector | 2612167.6 | 0 | 0 |  | 2612167.6 | 0 | 72346.76 | 219.59 | 263674.14 | 336240.49 | 2275927.11 | 12.87%
P-00223 Historic Surveys | 47195 | 0 | 0 |  | 47195 | 0 | 0 | 0 | 39940 | 39940 | 7255 | 84.63%
P-00272 VDOT URBAN ALLOCATION - First Cities | 666661.5 | 0 | 0 |  | 666661.5 | 0 | 0 | 0 | 0 | 0 | 666661.5 | 0%
P-00335 New Sidewalks | 727161.74 | 300000 | 0 | 300000 | 1027161.74 | 0 | 265946.08 | 0 | 232362.94 | 498309.02 | 528852.72 | 48.51%
P-00339 McIntire Road Ext | 683841.38 | 0 | 0 |  | 683841.38 | 0 | 46.06 | 0 | 0 | 46.06 | 683795.32 | 0.006735%
P-00341 Neighborhood Drainage Projects | 53644.95 | 175000 | 0 | 175000 | 228644.95 | 30.93 | 101908.13 | 0 | 30229 | 132137.13 | 96507.82 | 57.79%
P-00353 Eastern Connector Project | 4656.5 | 0 | 0 |  | 4656.5 | 0 | 0 | 0 | 0 | 0 | 4656.5 | 0%
P-00373 Neighborhood Leadership Institute | 5327.32 | 0 | 0 |  | 5327.32 | 0 | 0 | 0 | 0 | 0 | 5327.32 | 0%
P-00436 Belmont Bridge Replacement | 1653057.28 | 0 | 0 |  | 1653057.28 | 88840 | 234655 | 9976 | 476398 | 721029 | 932028.28 | 43.62%
P-00438 Neighborhood CIP Funds | 141852.95 | 0 | 0 |  | 141852.95 | 0 | 8843.86 | 0 | 0 | 8843.86 | 133009.09 | 6.235%
P-00439 Charlottesville Housing Fund | 345503.86 | 1200000 | -106439.88 | 1200000 | 1439063.98 | 668.63 | 96350.62 | 0 | 66084.67 | 162435.29 | 1276628.69 | 11.29%
P-00484 New Historic Surveys | 26750 | 0 | 0 |  | 26750 | 0 | 0 | 0 | 0 | 0 | 26750 | 0%
P-00491 Citywide ADA - Sidewalks and Curbs | 159982.04 | 100000 | 0 | 100000 | 259982.04 | 0 | 6746.49 | 0 | 0 | 6746.49 | 253235.55 | 2.595%
P-00502 Safe Routes-Burnley-Moran | 328280 | 0 | 0 |  | 328280 | 0 | 0 | 0 | 0 | 0 | 328280 | 0%
P-00507 HOME Projects Local Funding Match | 39348.65 | 0 | 0 |  | 39348.65 | 0 | 0 | 0 | 0 | 0 | 39348.65 | 0%
P-00508 Pedestrian Safety Projects | 68804.54 | 0 | 0 |  | 68804.54 | 0 | 0 | 0 | 22920 | 22920 | 45884.54 | 33.31%
P-00511 Old Lynchburg Road | 429608.21 | 0 | 0 |  | 429608.21 | 0 | 7952 | 0 | 411311 | 419263 | 10345.21 | 97.59%
P-00520 Home Energy Conservation Program | 241393.08 | 0 | 0 |  | 241393.08 | 0 | 0 | 0 | 116393.08 | 116393.08 | 125000 | 48.22%
P-00533 Bicycle Infrastructure Improvements | 1295 | 50000 | 0 | 50000 | 51295 | 0 | 0 | 0 | 15800 | 15800 | 35495 | 30.8%
P-00539 Corner Renovation | 78802.45 | 0 | 0 |  | 78802.45 | 0 | 42703.39 | 0 | 28010.73 | 70714.12 | 8088.33 | 89.74%
P-00579 Ecoremod | 149440.6 | 0 | 130000 |  | 279440.6 | 0 | 77589.72 | 0 | 59848 | 137437.72 | 142002.88 | 49.18%
P-00580 SRO | 23560.12 | 0 | -23560.12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
P-00585 Roy's Place Improvements | 7726 | 0 | 0 |  | 7726 | 0 | 0 | 0 | 7726 | 7726 | 0 | 100%
P-00593 Belmont Commercial Neighborhood Improvements | 0 | 200000 | 0 | 200000 | 200000 | 0 | 987.5 | 0 | 18762.5 | 19750 | 180250 | 9.875%
P-00598 Monet Vista Trail Drainage | 182000 | 0 | 0 |  | 182000 | 0 | 145205.26 | 0 | 36487.79 | 181693.05 | 306.95 | 99.83%
P-00612 Schenk's Branch Stormwater Repair | 0 | 0 | 500000 |  | 500000 | 0 | 0 | 0 | 0 | 0 | 500000 | 0%
SS-008 Traffic Improvements | 255184.09 | 100000 | 0 | 100000 | 355184.09 | 4311 | 56883.42 | 0 | 65411.83 | 122295.25 | 232888.84 | 34.43%
TOTAL |  |  |  | 33854150 | 92813802.19 | 1347016.5 | 11925447.79 | 11424.55 | 14628508.07 | 26565380.41 | 66248421.78 | 28.62%
(1) - Included in Current Budget column.