## Sheet1
PROJECT TRACKING REPORT
Project Name: Police Station Renovation
Approved Total Project Budget (pre-award) |  | 515666
Source: | FY10 Budget
Total Contract Price(s): |  | 502723.21
Breakdown (if applicable): | HEERY International - Design Fees | 58138
| HEERY International - Project Management | 25460
| Legal Ads | 60
| Construction (Blue Frog Construction, LLC): | 135988.17 | Original contract
| Blue Frog Change Order #1 | 1450 | Cabinet upgrades
| Blue Frog Change Order #2 | 3850 | Electrical outlets/boxes - low voltage
| Blue Frog Change Order #3 | 21682.4 | Replacement of carpet and VCT
| Blue Frog Change Order #4 | 5880.21 | Misc. doors, outlets, lights, etc.
| Blue Frog Change Order #5 | 0 | Crossroads C/O
| Blue Frog Change Order #6 | 828 | Sargent locksets
| Blue Frog Change Order #7 | 982 | Light switch, sprinkler heads, fire sign
| Office Furniture (Minton Jones) | 62299.7 | Original contract
| Low Voltage (Total Tehnology Group, LLC) | 167783 | Original contract
| Total Technology Change Order #1 | 2116.73 | Misc. - approved 1/15/10
| Total Technology Change Order #2 | 239 | Misc. - approved 2/18/10
| American Integrated Services | 15966 | Servers and switches
502723.21
Balance: |  | 12942.79
Revenue Sources: | 2005 SPLOST | 515666
Revision Date: 3/11/10